## Summary
Mutum Bridge (A)
| Start of project | 2012-01-01
| End of Project(Target) | 2012-04-01
| Duration of project | 56 weeks
| Activity and their duration | As Shown in chart
Uncertainities
a | River Bank being unstable and abetment would take time from 6 to 21 weeks
b | Unavailabilty of cranes till april end(16 weeks) and alternative machines would cost 20000 per week(1in 15 chance)
Solution
| Proposal | 1 | 2a | 2b | 2c | 3 | 3 | 4a | 4c
| Activity | 27 | 5 | 6 | 7 | 18 | 18 | 20 | 22
| Original Duration | 5 | 4 | 6 | 4 | 10 | 10 | 3 | 3
| New Duration | 2 | 2 | 3 | 2 | 7 | 5 | 1.5 | 1.5
| Cost | 4000 | 40000 | 40000 | 40000 | 1200000 | 2000000 | 400000 | 400000
Proposal
| Delay | 1 | 2a | 2b | 2c | 3 | 3 | 4a | 4c | Target Duration | Cost during Crashing | Delay | Penalty (weeks) | Penalty | Extra Cost | For Actual Probabilty (refer Monte Carlo Stimulation)
Abetment 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | -3 | 0 | 0 | 0
| 21 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 44000 | -1 | 0 | 0 | 44000
Abetment2 | 16 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 56 | 1244000 | 0 | 0 | 0 | 1244000
| 21 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 59 | 2044000 | 3 | 3 | 3600000 | 5644000
Abetment 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | -1 | 0 | 0 | 0
| 21 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 57 | 44000 | 1 | 1 | 1200000 | 1244000
Abetment 1&2 | 16 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 56 | 1244000 | 0 | 0 | 0 | 1244000
| 21 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 59 | 2044000 | 3 | 3 | 3600000 | 5644000
Abetment 1&3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | -1 | 0 | 0 | 0
| 21 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 57 | 44000 | 1 | 1 | 1200000 | 1244000
Abetment 2&3 | 16 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 56 | 1284000 | 0 | 0 | 0 | 1284000
| 21 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 59 | 2044000 | 3 | 3 | 3600000 | 5644000
Abetment 1,2,3 | 16 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 56 | 1284000 | 0 | 0 | 0 | 1284000
| 21 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 59 | 2044000 | 3 | 3 | 3600000 | 5644000
Case b
Except when Abetment 1,2 and 3 is being delayd because of ground activity, we will need to start project by week 9 to avoid penalty. Hence we require alternative machines for 16-9 ie 7 weeks
| Penalty Amount | 1400000
| Probality of it occuring all three Simultaeneously |  | 0.12
| Probabilty of needing alternate machine |  | 0.058667

## Ideal Time
|  | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  | 0 | 6 | 6 | 6 | 7 | 7 | 7 | 10 | 12 | 10 | 11 | 14 | 11 | 12 | 15 | 12 | 16 | 21 | 16 | 23 | 31 | 23 | 26 | 36 | 26 | 29 | 39 | 41 | 45 | 46 | 53 | 617
1 | Preparatory work and move in | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | >= | 6
|  | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | >= | 6
|  | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | >= | 6
2 | Mobilize Pile Rig 1 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
3 | Mobilize Pile Rig 2 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
4 | Mobilize Pile rig 4 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
5 | Excavate Abutment 1 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
6 | Excavate Abutment 2 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | >= | 6
7 | Excavate Abutment 3 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
8 | Drive Piles abutment 1 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 1
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
9 | Drive Piles Abutment 2 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
10 | Drive Piles Abutment 3 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 1
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
11 | Demobilize Pile Rig 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
12 | Demobilize Pile Rig 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
13 | Demobilize Pile Rig 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
14 | Forms, Pour and strip Footing 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
15 | Forms, Pour and strip Footing 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | >= | 7
16 | Forms, Pour and strip Footing 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
17 | Form Pour and Strip Abutment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | >= | 7
18 | Form Pour and Strip Abutment 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
19 | Form Pour and Strip Abutment 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | >= | 7
20 | Backfill Abutment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | >= | 3
21 | Backfill Abutment 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
22 | Backfill Abutment 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | >= | 3
23 | Set Girders and Forms Deck 1-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | >= | 6
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | -2 | >= | 6
24 | Set Girders and Forms Deck 2-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | >= | 8
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | >= | 8
25 | Pour Deck | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 12 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 2 | >= | 2
26 | Saw Joints | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 4 | >= | 4
27 | Strip Deck and Rub Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 5 | >= | 5
28 | Clean up and Final inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 8 | >= | 7
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | >= | 7

## Montecarlo Stimulation
Risk Analysis
1 | 50 % of the case, there will be unstable ground which will add 10 weeks more and up to 15 weeks. So, we take 50 % percent probabilty that duration will be 6 weeks, 8.33 % it will be 10,11,12,13,14 and 15 weeks)
2 | 1 in 15 case that alternative machines will be used for cranes and cost of these machines will be 20000. Since it does not affect the duration of the project, we ignore in time series calculation.
|  | Duration |  |  | Calculation |  |  | Calculation
| Sr No. | Abutment 1 | Abutment2 | Abutment3 | Abutment 1 | Abutment2 | Abutment3 | Abutment 1 | Abutment2 | Abutment3 | Values | Duration
| 1 | 19 | 18 | 18 | 9 | 12 | 11 | 10 | 9 | 9 | 1 | 6
| 2 | 17 | 20 | 19 | 8 | 9 | 1 | 8 | 11 | 10 | 2 | 6
| 3 | 6 | 6 | 6 | 1 | 1 | 8 | 6 | 3 | 6 | 3 | 6
| 4 | 6 | 6 | 6 | 4 | 6 | 3 | 5 | 3 | 4 | 4 | 6
| 5 | 19 | 6 | 6 | 2 | 2 | 12 | 10 | 2 | 4 | 5 | 6
| 6 | 6 | 6 | 18 | 2 | 4 | 5 | 6 | 1 | 9 | 6 | 6
| 7 | 18 | 20 | 16 | 3 | 6 | 5 | 9 | 11 | 7 | 7 | 16
| 8 | 6 | 21 | 20 | 6 | 4 | 10 | 5 | 12 | 11 | 8 | 17
| 9 | 16 | 6 | 19 | 1 | 2 | 12 | 7 | 6 | 10 | 9 | 18
| 10 | 19 | 6 | 6 | 6 | 10 | 3 | 10 | 4 | 3 | 10 | 19
| 11 | 20 | 17 | 6 | 5 | 6 | 4 | 11 | 8 | 4 | 11 | 20
| 12 | 20 | 20 | 21 | 10 | 5 | 2 | 11 | 11 | 12 | 12 | 21
| 13 | 21 | 16 | 6 | 4 | 5 | 1 | 12 | 7 | 4
| 14 | 6 | 19 | 6 | 10 | 11 | 4 | 6 | 10 | 1 |  | Abetment1 | Abetment2 | Abetment3
| 15 | 21 | 6 | 20 | 2 | 10 | 4 | 12 | 1 | 11 | Mean | 12.314 | 12.171 | 12.117
| 16 | 16 | 6 | 18 | 9 | 7 | 12 | 7 | 3 | 9 | Deviation | 6.2966 | 6.406 | 6.3565
| 17 | 17 | 6 | 6 | 1 | 9 | 11 | 8 | 6 | 2
| 18 | 18 | 6 | 6 | 10 | 8 | 1 | 9 | 6 | 2
| 19 | 17 | 6 | 20 | 9 | 5 | 5 | 8 | 6 | 11
| 20 | 18 | 6 | 6 | 10 | 9 | 2 | 9 | 6 | 2
| 21 | 17 | 6 | 6 | 8 | 12 | 2 | 8 | 5 | 2
| 22 | 20 | 20 | 16 | 12 | 3 | 7 | 11 | 11 | 7
| 23 | 6 | 17 | 21 | 2 | 2 | 1 | 2 | 8 | 12
| 24 | 20 | 6 | 21 | 5 | 7 | 4 | 11 | 4 | 12
| 25 | 18 | 21 | 18 | 8 | 11 | 10 | 9 | 12 | 9
| 26 | 6 | 6 | 6 | 9 | 9 | 9 | 1 | 1 | 6
| 27 | 6 | 6 | 17 | 4 | 1 | 11 | 6 | 3 | 8
| 28 | 6 | 6 | 18 | 3 | 11 | 7 | 4 | 1 | 9
| 29 | 6 | 6 | 19 | 6 | 12 | 11 | 3 | 5 | 10
| 30 | 21 | 17 | 6 | 11 | 7 | 7 | 12 | 8 | 6
| 31 | 17 | 19 | 6 | 3 | 5 | 2 | 8 | 10 | 6
| 32 | 17 | 16 | 6 | 10 | 6 | 7 | 8 | 7 | 3
| 33 | 6 | 6 | 16 | 3 | 9 | 3 | 6 | 3 | 7
| 34 | 18 | 6 | 6 | 3 | 4 | 9 | 9 | 1 | 4
| 35 | 18 | 17 | 16 | 1 | 9 | 7 | 9 | 8 | 7
| 36 | 18 | 6 | 16 | 10 | 6 | 1 | 9 | 1 | 7
| 37 | 19 | 6 | 6 | 7 | 5 | 8 | 10 | 2 | 6
| 38 | 6 | 21 | 6 | 12 | 8 | 12 | 4 | 12 | 1
| 39 | 6 | 6 | 6 | 9 | 9 | 6 | 5 | 4 | 3
| 40 | 6 | 21 | 6 | 8 | 1 | 4 | 2 | 12 | 4
| 41 | 17 | 18 | 18 | 11 | 10 | 1 | 8 | 9 | 9
| 42 | 19 | 18 | 6 | 10 | 2 | 2 | 10 | 9 | 5
| 43 | 6 | 6 | 6 | 9 | 5 | 6 | 6 | 1 | 1
| 44 | 6 | 6 | 19 | 3 | 9 | 11 | 4 | 1 | 10
| 45 | 19 | 6 | 17 | 2 | 2 | 12 | 10 | 6 | 8
| 46 | 19 | 6 | 6 | 10 | 5 | 6 | 10 | 3 | 1
| 47 | 6 | 18 | 6 | 11 | 5 | 11 | 4 | 9 | 6
| 48 | 16 | 6 | 6 | 2 | 10 | 3 | 7 | 2 | 6
| 49 | 17 | 20 | 6 | 6 | 6 | 2 | 8 | 11 | 1
| 50 | 6 | 6 | 17 | 7 | 6 | 4 | 6 | 4 | 8
| 51 | 6 | 6 | 6 | 2 | 10 | 6 | 6 | 1 | 3
| 52 | 20 | 18 | 19 | 2 | 9 | 1 | 11 | 9 | 10
| 53 | 17 | 16 | 16 | 1 | 4 | 10 | 8 | 7 | 7
| 54 | 6 | 16 | 6 | 2 | 12 | 7 | 4 | 7 | 6
| 55 | 6 | 6 | 6 | 10 | 1 | 7 | 5 | 6 | 1
| 56 | 18 | 21 | 6 | 4 | 4 | 9 | 9 | 12 | 2
| 57 | 6 | 21 | 21 | 5 | 5 | 7 | 2 | 12 | 12
| 58 | 6 | 6 | 6 | 2 | 5 | 6 | 1 | 4 | 5
| 59 | 16 | 6 | 17 | 10 | 9 | 4 | 7 | 3 | 8
| 60 | 6 | 6 | 20 | 4 | 4 | 3 | 5 | 2 | 11
| 61 | 17 | 16 | 6 | 4 | 6 | 8 | 8 | 7 | 5
| 62 | 16 | 21 | 17 | 9 | 6 | 1 | 7 | 12 | 8
| 63 | 16 | 6 | 6 | 9 | 5 | 12 | 7 | 6 | 6
| 64 | 16 | 6 | 6 | 6 | 4 | 12 | 7 | 4 | 4
| 65 | 6 | 6 | 6 | 8 | 8 | 4 | 3 | 4 | 2
| 66 | 6 | 6 | 6 | 11 | 10 | 6 | 4 | 1 | 4
| 67 | 17 | 6 | 6 | 9 | 7 | 4 | 8 | 2 | 4
| 68 | 19 | 18 | 6 | 12 | 8 | 10 | 10 | 9 | 5
| 69 | 6 | 21 | 19 | 12 | 3 | 10 | 1 | 12 | 10
| 70 | 19 | 6 | 6 | 11 | 4 | 1 | 10 | 5 | 2
| 71 | 6 | 19 | 17 | 7 | 9 | 7 | 4 | 10 | 8
| 72 | 17 | 6 | 20 | 9 | 4 | 6 | 8 | 4 | 11
| 73 | 6 | 21 | 6 | 2 | 10 | 5 | 3 | 12 | 5
| 74 | 6 | 6 | 6 | 9 | 10 | 8 | 6 | 4 | 4
| 75 | 20 | 6 | 18 | 7 | 3 | 4 | 11 | 4 | 9
| 76 | 20 | 6 | 6 | 10 | 7 | 10 | 11 | 2 | 1
| 77 | 6 | 6 | 21 | 7 | 4 | 4 | 6 | 4 | 12
| 78 | 20 | 18 | 6 | 6 | 11 | 7 | 11 | 9 | 6
| 79 | 16 | 19 | 17 | 12 | 3 | 1 | 7 | 10 | 8
| 80 | 6 | 6 | 6 | 3 | 8 | 9 | 3 | 2 | 6
| 81 | 6 | 21 | 18 | 1 | 7 | 6 | 2 | 12 | 9
| 82 | 6 | 18 | 6 | 11 | 12 | 7 | 2 | 9 | 6
| 83 | 6 | 6 | 20 | 9 | 10 | 12 | 2 | 4 | 11
| 84 | 17 | 19 | 6 | 1 | 11 | 8 | 8 | 10 | 3
| 85 | 6 | 6 | 17 | 1 | 1 | 9 | 3 | 2 | 8
| 86 | 6 | 6 | 6 | 9 | 10 | 6 | 1 | 5 | 4
| 87 | 6 | 6 | 16 | 8 | 5 | 2 | 3 | 2 | 7
| 88 | 6 | 16 | 19 | 1 | 7 | 11 | 3 | 7 | 10
| 89 | 6 | 16 | 21 | 8 | 8 | 8 | 3 | 7 | 12
| 90 | 16 | 6 | 20 | 9 | 1 | 11 | 7 | 1 | 11
| 91 | 17 | 20 | 6 | 8 | 5 | 4 | 8 | 11 | 3
| 92 | 6 | 6 | 6 | 6 | 3 | 6 | 1 | 5 | 3
| 93 | 16 | 21 | 20 | 9 | 5 | 12 | 7 | 12 | 11
| 94 | 6 | 20 | 19 | 10 | 1 | 5 | 2 | 11 | 10
| 95 | 6 | 20 | 20 | 3 | 2 | 12 | 2 | 11 | 11
| 96 | 20 | 17 | 6 | 3 | 7 | 12 | 11 | 8 | 2
| 97 | 19 | 20 | 6 | 7 | 8 | 3 | 10 | 11 | 4
| 98 | 6 | 16 | 21 | 7 | 8 | 9 | 5 | 7 | 12
| 99 | 6 | 6 | 6 | 7 | 4 | 7 | 5 | 2 | 6
| 100 | 6 | 20 | 6 | 6 | 9 | 9 | 4 | 11 | 3
| 101 | 19 | 6 | 16 | 6 | 4 | 5 | 10 | 3 | 7
| 102 | 17 | 17 | 6 | 7 | 12 | 10 | 8 | 8 | 3
| 103 | 17 | 21 | 16 | 6 | 10 | 11 | 8 | 12 | 7
| 104 | 6 | 21 | 17 | 5 | 6 | 8 | 1 | 12 | 8
| 105 | 6 | 6 | 6 | 10 | 5 | 11 | 1 | 6 | 5
| 106 | 6 | 6 | 21 | 4 | 5 | 10 | 4 | 4 | 12
| 107 | 6 | 6 | 6 | 2 | 10 | 4 | 6 | 6 | 4
| 108 | 16 | 21 | 21 | 7 | 6 | 8 | 7 | 12 | 12
| 109 | 6 | 16 | 17 | 4 | 7 | 12 | 5 | 7 | 8
| 110 | 6 | 21 | 17 | 8 | 8 | 1 | 6 | 12 | 8
| 111 | 18 | 21 | 6 | 1 | 3 | 1 | 9 | 12 | 4
| 112 | 6 | 18 | 16 | 9 | 2 | 9 | 3 | 9 | 7
| 113 | 6 | 21 | 19 | 11 | 9 | 12 | 3 | 12 | 10
| 114 | 6 | 21 | 16 | 12 | 1 | 3 | 1 | 12 | 7
| 115 | 6 | 18 | 16 | 9 | 2 | 12 | 4 | 9 | 7
| 116 | 6 | 21 | 6 | 4 | 7 | 12 | 2 | 12 | 2
| 117 | 20 | 6 | 6 | 2 | 8 | 6 | 11 | 3 | 5
| 118 | 6 | 6 | 17 | 5 | 4 | 3 | 4 | 1 | 8
| 119 | 21 | 19 | 16 | 8 | 6 | 2 | 12 | 10 | 7
| 120 | 6 | 6 | 19 | 9 | 12 | 12 | 6 | 5 | 10
| 121 | 6 | 6 | 6 | 11 | 4 | 8 | 4 | 3 | 2
| 122 | 6 | 16 | 6 | 5 | 11 | 7 | 5 | 7 | 2
| 123 | 6 | 6 | 21 | 12 | 9 | 9 | 6 | 4 | 12
| 124 | 16 | 6 | 6 | 2 | 11 | 12 | 7 | 5 | 4
| 125 | 18 | 6 | 6 | 3 | 9 | 3 | 9 | 6 | 4
| 126 | 6 | 17 | 6 | 2 | 3 | 5 | 2 | 8 | 6
| 127 | 19 | 20 | 6 | 5 | 1 | 2 | 10 | 11 | 4
| 128 | 19 | 6 | 20 | 10 | 11 | 6 | 10 | 1 | 11
| 129 | 6 | 6 | 6 | 11 | 5 | 4 | 5 | 1 | 2
| 130 | 6 | 6 | 16 | 8 | 4 | 5 | 4 | 6 | 7
| 131 | 18 | 21 | 19 | 5 | 2 | 8 | 9 | 12 | 10
| 132 | 6 | 19 | 6 | 1 | 10 | 1 | 4 | 10 | 2
| 133 | 16 | 20 | 6 | 4 | 9 | 9 | 7 | 11 | 1
| 134 | 21 | 6 | 21 | 7 | 1 | 7 | 12 | 4 | 12
| 135 | 6 | 6 | 17 | 9 | 5 | 7 | 4 | 2 | 8
| 136 | 6 | 16 | 20 | 12 | 7 | 7 | 5 | 7 | 11
| 137 | 21 | 18 | 21 | 9 | 10 | 4 | 12 | 9 | 12
| 138 | 18 | 6 | 6 | 9 | 6 | 12 | 9 | 2 | 1
| 139 | 6 | 6 | 6 | 4 | 11 | 12 | 6 | 4 | 3
| 140 | 6 | 6 | 18 | 11 | 1 | 3 | 3 | 6 | 9
| 141 | 6 | 6 | 6 | 10 | 8 | 7 | 1 | 6 | 1
| 142 | 19 | 21 | 19 | 7 | 8 | 4 | 10 | 12 | 10
| 143 | 6 | 6 | 6 | 1 | 7 | 8 | 1 | 5 | 2
| 144 | 17 | 6 | 6 | 9 | 11 | 5 | 8 | 4 | 1
| 145 | 6 | 6 | 19 | 8 | 6 | 10 | 3 | 5 | 10
| 146 | 18 | 20 | 6 | 3 | 9 | 3 | 9 | 11 | 5
| 147 | 6 | 6 | 6 | 2 | 6 | 4 | 3 | 1 | 5
| 148 | 6 | 6 | 6 | 3 | 11 | 1 | 1 | 2 | 5
| 149 | 19 | 17 | 16 | 11 | 9 | 8 | 10 | 8 | 7
| 150 | 6 | 20 | 20 | 1 | 11 | 12 | 4 | 11 | 11
| 151 | 17 | 19 | 6 | 9 | 7 | 4 | 8 | 10 | 1
| 152 | 6 | 19 | 6 | 11 | 12 | 1 | 1 | 10 | 1
| 153 | 20 | 6 | 19 | 7 | 10 | 1 | 11 | 3 | 10
| 154 | 17 | 6 | 6 | 11 | 10 | 8 | 8 | 5 | 1
| 155 | 16 | 20 | 6 | 3 | 3 | 9 | 7 | 11 | 6
| 156 | 6 | 21 | 6 | 2 | 4 | 5 | 5 | 12 | 1
| 157 | 17 | 18 | 6 | 4 | 6 | 3 | 8 | 9 | 3
| 158 | 6 | 18 | 19 | 6 | 8 | 5 | 1 | 9 | 10
| 159 | 6 | 6 | 16 | 11 | 8 | 3 | 1 | 6 | 7
| 160 | 19 | 6 | 20 | 8 | 8 | 3 | 10 | 6 | 11
| 161 | 6 | 6 | 16 | 8 | 6 | 9 | 5 | 3 | 7
| 162 | 6 | 6 | 6 | 3 | 11 | 9 | 4 | 2 | 2
| 163 | 21 | 16 | 16 | 6 | 12 | 2 | 12 | 7 | 7
| 164 | 6 | 17 | 17 | 7 | 1 | 11 | 2 | 8 | 8
| 165 | 6 | 6 | 20 | 2 | 9 | 4 | 1 | 5 | 11
| 166 | 6 | 19 | 19 | 8 | 6 | 1 | 4 | 10 | 10
| 167 | 19 | 6 | 16 | 10 | 6 | 11 | 10 | 4 | 7
| 168 | 19 | 6 | 6 | 2 | 7 | 10 | 10 | 4 | 4
| 169 | 6 | 16 | 6 | 4 | 4 | 6 | 2 | 7 | 3
| 170 | 20 | 19 | 16 | 10 | 12 | 7 | 11 | 10 | 7
| 171 | 6 | 6 | 6 | 10 | 12 | 6 | 5 | 5 | 3
| 172 | 6 | 21 | 16 | 12 | 11 | 3 | 1 | 12 | 7
| 173 | 16 | 20 | 6 | 7 | 5 | 11 | 7 | 11 | 2
| 174 | 6 | 6 | 6 | 1 | 10 | 10 | 1 | 2 | 2
| 175 | 17 | 6 | 6 | 4 | 8 | 1 | 8 | 6 | 1
| 176 | 6 | 19 | 6 | 6 | 3 | 12 | 4 | 10 | 3
| 177 | 21 | 6 | 16 | 10 | 5 | 6 | 12 | 5 | 7
| 178 | 17 | 6 | 19 | 12 | 8 | 1 | 8 | 2 | 10
| 179 | 16 | 6 | 21 | 2 | 11 | 2 | 7 | 3 | 12
| 180 | 6 | 18 | 6 | 11 | 5 | 9 | 6 | 9 | 3
| 181 | 6 | 21 | 6 | 11 | 8 | 4 | 1 | 12 | 2
| 182 | 6 | 21 | 6 | 4 | 7 | 1 | 5 | 12 | 5
| 183 | 6 | 21 | 6 | 8 | 6 | 8 | 4 | 12 | 2
| 184 | 18 | 6 | 16 | 3 | 1 | 10 | 9 | 4 | 7
| 185 | 6 | 6 | 18 | 9 | 6 | 6 | 4 | 3 | 9
| 186 | 16 | 6 | 17 | 8 | 7 | 11 | 7 | 5 | 8
| 187 | 20 | 6 | 18 | 5 | 5 | 2 | 11 | 4 | 9
| 188 | 16 | 21 | 20 | 10 | 7 | 2 | 7 | 12 | 11
| 189 | 6 | 18 | 6 | 5 | 11 | 11 | 3 | 9 | 3
| 190 | 6 | 6 | 6 | 12 | 11 | 7 | 5 | 5 | 1
| 191 | 6 | 6 | 19 | 3 | 10 | 2 | 5 | 4 | 10
| 192 | 18 | 6 | 6 | 3 | 2 | 8 | 9 | 3 | 5
| 193 | 17 | 21 | 6 | 6 | 1 | 4 | 8 | 12 | 5
| 194 | 6 | 17 | 6 | 10 | 12 | 4 | 2 | 8 | 1
| 195 | 18 | 6 | 18 | 5 | 6 | 7 | 9 | 4 | 9
| 196 | 6 | 18 | 18 | 3 | 10 | 11 | 6 | 9 | 9
| 197 | 6 | 6 | 6 | 1 | 12 | 8 | 1 | 1 | 5
| 198 | 6 | 19 | 6 | 1 | 5 | 1 | 1 | 10 | 4
| 199 | 6 | 20 | 20 | 9 | 4 | 10 | 4 | 11 | 11
| 200 | 18 | 16 | 6 | 2 | 6 | 6 | 9 | 7 | 6
| 201 | 17 | 19 | 6 | 6 | 3 | 11 | 8 | 10 | 5
| 202 | 18 | 6 | 6 | 9 | 8 | 8 | 9 | 4 | 6
| 203 | 18 | 6 | 16 | 4 | 1 | 2 | 9 | 6 | 7
| 204 | 6 | 16 | 21 | 3 | 1 | 4 | 2 | 7 | 12
| 205 | 16 | 19 | 20 | 8 | 12 | 1 | 7 | 10 | 11
| 206 | 20 | 21 | 18 | 12 | 1 | 10 | 11 | 12 | 9
| 207 | 16 | 6 | 6 | 12 | 12 | 12 | 7 | 2 | 1
| 208 | 6 | 16 | 6 | 10 | 6 | 4 | 6 | 7 | 2
| 209 | 18 | 6 | 6 | 9 | 11 | 10 | 9 | 1 | 3
| 210 | 19 | 6 | 6 | 9 | 8 | 4 | 10 | 5 | 4
| 211 | 6 | 6 | 6 | 5 | 1 | 10 | 2 | 4 | 6
| 212 | 6 | 6 | 17 | 1 | 12 | 9 | 5 | 5 | 8
| 213 | 16 | 6 | 6 | 10 | 6 | 12 | 7 | 4 | 5
| 214 | 19 | 21 | 6 | 2 | 7 | 4 | 10 | 12 | 1
| 215 | 17 | 17 | 20 | 3 | 9 | 1 | 8 | 8 | 11
| 216 | 19 | 6 | 6 | 2 | 1 | 1 | 10 | 3 | 5
| 217 | 20 | 19 | 16 | 2 | 6 | 8 | 11 | 10 | 7
| 218 | 19 | 6 | 6 | 2 | 10 | 8 | 10 | 1 | 4
| 219 | 6 | 20 | 21 | 8 | 1 | 3 | 4 | 11 | 12
| 220 | 19 | 20 | 6 | 4 | 1 | 2 | 10 | 11 | 2
| 221 | 20 | 16 | 21 | 10 | 3 | 8 | 11 | 7 | 12
| 222 | 6 | 6 | 6 | 6 | 9 | 8 | 1 | 1 | 6
| 223 | 17 | 16 | 18 | 11 | 3 | 4 | 8 | 7 | 9
| 224 | 6 | 20 | 6 | 11 | 12 | 9 | 5 | 11 | 2
| 225 | 19 | 6 | 6 | 3 | 7 | 5 | 10 | 1 | 2
| 226 | 6 | 21 | 6 | 11 | 2 | 3 | 4 | 12 | 5
| 227 | 6 | 18 | 18 | 2 | 3 | 2 | 4 | 9 | 9
| 228 | 21 | 19 | 21 | 9 | 11 | 11 | 12 | 10 | 12
| 229 | 6 | 6 | 6 | 6 | 4 | 3 | 6 | 1 | 4
| 230 | 6 | 6 | 6 | 10 | 1 | 4 | 1 | 2 | 4
| 231 | 17 | 6 | 18 | 12 | 10 | 3 | 8 | 3 | 9
| 232 | 6 | 6 | 6 | 4 | 1 | 4 | 3 | 1 | 6
| 233 | 6 | 18 | 18 | 3 | 11 | 5 | 5 | 9 | 9
| 234 | 6 | 19 | 6 | 11 | 10 | 9 | 5 | 10 | 3
| 235 | 6 | 6 | 17 | 3 | 2 | 10 | 5 | 6 | 8
| 236 | 6 | 21 | 6 | 12 | 8 | 10 | 3 | 12 | 3
| 237 | 21 | 16 | 18 | 8 | 12 | 1 | 12 | 7 | 9
| 238 | 6 | 6 | 6 | 1 | 7 | 5 | 6 | 5 | 2
| 239 | 16 | 6 | 6 | 5 | 5 | 5 | 7 | 5 | 1
| 240 | 6 | 6 | 6 | 4 | 1 | 3 | 6 | 1 | 6
| 241 | 16 | 6 | 18 | 3 | 12 | 5 | 7 | 4 | 9
| 242 | 6 | 6 | 20 | 8 | 4 | 8 | 3 | 6 | 11
| 243 | 6 | 21 | 6 | 6 | 10 | 4 | 6 | 12 | 6
| 244 | 6 | 6 | 6 | 5 | 2 | 7 | 2 | 4 | 2
| 245 | 19 | 17 | 6 | 10 | 4 | 8 | 10 | 8 | 2
| 246 | 6 | 6 | 6 | 3 | 7 | 12 | 2 | 4 | 6
| 247 | 19 | 6 | 19 | 9 | 2 | 9 | 10 | 5 | 10
| 248 | 6 | 20 | 20 | 10 | 11 | 5 | 6 | 11 | 11
| 249 | 16 | 6 | 6 | 11 | 4 | 9 | 7 | 5 | 1
| 250 | 18 | 6 | 6 | 12 | 1 | 9 | 9 | 6 | 6
| 251 | 6 | 18 | 19 | 6 | 7 | 6 | 5 | 9 | 10
| 252 | 6 | 6 | 19 | 5 | 4 | 7 | 2 | 2 | 10
| 253 | 20 | 6 | 18 | 5 | 2 | 1 | 11 | 6 | 9
| 254 | 6 | 20 | 6 | 9 | 9 | 10 | 1 | 11 | 1
| 255 | 6 | 6 | 21 | 12 | 2 | 6 | 1 | 5 | 12
| 256 | 20 | 19 | 20 | 2 | 5 | 12 | 11 | 10 | 11
| 257 | 21 | 20 | 6 | 8 | 7 | 8 | 12 | 11 | 6
| 258 | 6 | 6 | 6 | 10 | 6 | 9 | 5 | 6 | 5
| 259 | 6 | 19 | 6 | 3 | 5 | 2 | 6 | 10 | 6
| 260 | 20 | 19 | 16 | 7 | 10 | 9 | 11 | 10 | 7
| 261 | 16 | 16 | 6 | 1 | 12 | 10 | 7 | 7 | 2
| 262 | 16 | 17 | 6 | 7 | 6 | 9 | 7 | 8 | 4
| 263 | 6 | 20 | 6 | 7 | 6 | 5 | 3 | 11 | 5
| 264 | 20 | 6 | 6 | 1 | 3 | 2 | 11 | 6 | 2
| 265 | 6 | 18 | 16 | 7 | 11 | 3 | 3 | 9 | 7
| 266 | 6 | 20 | 19 | 6 | 2 | 9 | 6 | 11 | 10
| 267 | 21 | 21 | 20 | 9 | 1 | 7 | 12 | 12 | 11
| 268 | 17 | 6 | 6 | 3 | 12 | 12 | 8 | 5 | 5
| 269 | 17 | 18 | 19 | 10 | 12 | 6 | 8 | 9 | 10
| 270 | 19 | 17 | 16 | 7 | 7 | 7 | 10 | 8 | 7
| 271 | 18 | 20 | 20 | 1 | 5 | 2 | 9 | 11 | 11
| 272 | 17 | 6 | 6 | 7 | 7 | 8 | 8 | 3 | 2
| 273 | 6 | 20 | 20 | 12 | 7 | 8 | 3 | 11 | 11
| 274 | 18 | 6 | 20 | 10 | 10 | 9 | 9 | 6 | 11
| 275 | 6 | 19 | 6 | 1 | 1 | 9 | 4 | 10 | 6
| 276 | 6 | 16 | 6 | 2 | 2 | 6 | 6 | 7 | 6
| 277 | 18 | 6 | 19 | 12 | 11 | 12 | 9 | 4 | 10
| 278 | 6 | 18 | 6 | 8 | 12 | 3 | 3 | 9 | 5
| 279 | 16 | 6 | 6 | 2 | 3 | 7 | 7 | 2 | 1
| 280 | 6 | 20 | 6 | 9 | 9 | 6 | 4 | 11 | 4
| 281 | 6 | 17 | 6 | 10 | 7 | 10 | 2 | 8 | 5
| 282 | 16 | 16 | 21 | 4 | 10 | 8 | 7 | 7 | 12
| 283 | 6 | 6 | 6 | 4 | 7 | 10 | 5 | 1 | 6
| 284 | 21 | 19 | 6 | 12 | 5 | 4 | 12 | 10 | 5
| 285 | 18 | 6 | 6 | 5 | 7 | 12 | 9 | 6 | 5
| 286 | 6 | 16 | 19 | 8 | 3 | 7 | 6 | 7 | 10
| 287 | 16 | 16 | 17 | 2 | 2 | 12 | 7 | 7 | 8
| 288 | 19 | 6 | 6 | 4 | 11 | 3 | 10 | 1 | 6
| 289 | 6 | 6 | 18 | 11 | 8 | 4 | 2 | 5 | 9
| 290 | 6 | 6 | 6 | 7 | 1 | 7 | 4 | 6 | 4
| 291 | 6 | 6 | 18 | 3 | 3 | 8 | 2 | 5 | 9
| 292 | 19 | 20 | 18 | 6 | 6 | 11 | 10 | 11 | 9
| 293 | 21 | 6 | 6 | 10 | 4 | 8 | 12 | 1 | 6
| 294 | 6 | 6 | 6 | 6 | 6 | 4 | 5 | 4 | 2
| 295 | 6 | 19 | 6 | 9 | 10 | 4 | 5 | 10 | 3
| 296 | 6 | 6 | 17 | 11 | 11 | 1 | 6 | 2 | 8
| 297 | 19 | 17 | 18 | 1 | 7 | 9 | 10 | 8 | 9
| 298 | 16 | 19 | 6 | 10 | 6 | 1 | 7 | 10 | 1
| 299 | 20 | 19 | 16 | 2 | 2 | 4 | 11 | 10 | 7
| 300 | 19 | 6 | 6 | 10 | 7 | 4 | 10 | 5 | 1
| 301 | 6 | 17 | 6 | 6 | 10 | 8 | 4 | 8 | 3
| 302 | 6 | 6 | 17 | 8 | 9 | 8 | 1 | 5 | 8
| 303 | 6 | 19 | 20 | 3 | 2 | 7 | 2 | 10 | 11
| 304 | 6 | 6 | 6 | 2 | 8 | 5 | 1 | 1 | 2
| 305 | 16 | 18 | 6 | 11 | 10 | 8 | 7 | 9 | 6
| 306 | 6 | 18 | 17 | 12 | 11 | 6 | 5 | 9 | 8
| 307 | 6 | 6 | 6 | 11 | 8 | 2 | 6 | 2 | 6
| 308 | 21 | 6 | 6 | 4 | 7 | 2 | 12 | 2 | 3
| 309 | 6 | 17 | 19 | 2 | 1 | 3 | 6 | 8 | 10
| 310 | 6 | 17 | 16 | 6 | 3 | 2 | 1 | 8 | 7
| 311 | 19 | 20 | 6 | 9 | 3 | 4 | 10 | 11 | 5
| 312 | 19 | 21 | 18 | 11 | 2 | 11 | 10 | 12 | 9
| 313 | 6 | 6 | 17 | 8 | 1 | 5 | 2 | 1 | 8
| 314 | 21 | 6 | 18 | 4 | 10 | 10 | 12 | 6 | 9
| 315 | 6 | 21 | 18 | 11 | 11 | 5 | 5 | 12 | 9
| 316 | 6 | 21 | 17 | 1 | 11 | 10 | 2 | 12 | 8
| 317 | 19 | 6 | 6 | 11 | 4 | 3 | 10 | 6 | 4
| 318 | 19 | 16 | 19 | 9 | 9 | 6 | 10 | 7 | 10
| 319 | 20 | 6 | 16 | 8 | 12 | 5 | 11 | 3 | 7
| 320 | 6 | 18 | 6 | 4 | 12 | 1 | 3 | 9 | 4
| 321 | 16 | 6 | 6 | 5 | 5 | 12 | 7 | 4 | 3
| 322 | 19 | 17 | 18 | 5 | 6 | 11 | 10 | 8 | 9
| 323 | 20 | 21 | 20 | 10 | 2 | 2 | 11 | 12 | 11
| 324 | 6 | 16 | 17 | 12 | 11 | 1 | 6 | 7 | 8
| 325 | 16 | 6 | 6 | 7 | 11 | 7 | 7 | 2 | 3
| 326 | 6 | 6 | 16 | 5 | 3 | 8 | 6 | 2 | 7
| 327 | 18 | 6 | 20 | 10 | 11 | 3 | 9 | 2 | 11
| 328 | 20 | 6 | 6 | 4 | 6 | 1 | 11 | 5 | 3
| 329 | 16 | 20 | 6 | 5 | 10 | 7 | 7 | 11 | 6
| 330 | 6 | 6 | 17 | 6 | 4 | 6 | 3 | 2 | 8
| 331 | 18 | 21 | 6 | 11 | 9 | 10 | 9 | 12 | 1
| 332 | 16 | 20 | 19 | 12 | 3 | 4 | 7 | 11 | 10
| 333 | 19 | 18 | 6 | 4 | 9 | 1 | 10 | 9 | 3
| 334 | 21 | 21 | 6 | 1 | 2 | 4 | 12 | 12 | 6
| 335 | 6 | 6 | 18 | 10 | 7 | 9 | 2 | 4 | 9
| 336 | 19 | 6 | 21 | 8 | 1 | 8 | 10 | 5 | 12
| 337 | 6 | 18 | 21 | 6 | 2 | 8 | 5 | 9 | 12
| 338 | 20 | 6 | 21 | 12 | 9 | 8 | 11 | 2 | 12
| 339 | 16 | 17 | 6 | 3 | 5 | 12 | 7 | 8 | 5
| 340 | 20 | 6 | 6 | 3 | 2 | 3 | 11 | 1 | 2
| 341 | 16 | 6 | 19 | 3 | 4 | 3 | 7 | 1 | 10
| 342 | 18 | 20 | 6 | 7 | 10 | 12 | 9 | 11 | 2
| 343 | 6 | 6 | 21 | 10 | 11 | 4 | 6 | 4 | 12
| 344 | 6 | 6 | 6 | 1 | 2 | 6 | 6 | 4 | 6
| 345 | 18 | 17 | 6 | 11 | 6 | 11 | 9 | 8 | 6
| 346 | 21 | 16 | 6 | 12 | 12 | 12 | 12 | 7 | 6
| 347 | 18 | 16 | 6 | 2 | 6 | 12 | 9 | 7 | 3
| 348 | 6 | 6 | 6 | 6 | 5 | 1 | 5 | 2 | 4
| 349 | 19 | 19 | 21 | 2 | 9 | 7 | 10 | 10 | 12
| 350 | 6 | 6 | 17 | 10 | 6 | 12 | 1 | 1 | 8
| 351 | 18 | 6 | 19 | 9 | 1 | 1 | 9 | 4 | 10
| 352 | 6 | 18 | 6 | 7 | 9 | 5 | 1 | 9 | 3
| 353 | 6 | 6 | 18 | 3 | 1 | 6 | 3 | 2 | 9
| 354 | 16 | 18 | 17 | 9 | 8 | 10 | 7 | 9 | 8
| 355 | 16 | 6 | 20 | 2 | 7 | 8 | 7 | 6 | 11
| 356 | 20 | 21 | 6 | 5 | 7 | 5 | 11 | 12 | 6
| 357 | 6 | 6 | 20 | 12 | 7 | 1 | 1 | 6 | 11
| 358 | 6 | 6 | 20 | 11 | 10 | 9 | 4 | 5 | 11
| 359 | 6 | 17 | 19 | 7 | 12 | 6 | 5 | 8 | 10
| 360 | 18 | 6 | 6 | 12 | 6 | 9 | 9 | 6 | 4
| 361 | 20 | 16 | 6 | 6 | 11 | 11 | 11 | 7 | 5
| 362 | 18 | 21 | 16 | 1 | 5 | 3 | 9 | 12 | 7
| 363 | 21 | 6 | 20 | 4 | 11 | 11 | 12 | 2 | 11
| 364 | 19 | 6 | 18 | 4 | 11 | 10 | 10 | 1 | 9
| 365 | 6 | 6 | 16 | 4 | 3 | 10 | 3 | 2 | 7
| 366 | 19 | 6 | 6 | 7 | 6 | 11 | 10 | 2 | 2
| 367 | 19 | 6 | 19 | 6 | 8 | 1 | 10 | 5 | 10
| 368 | 16 | 16 | 20 | 8 | 8 | 1 | 7 | 7 | 11
| 369 | 21 | 6 | 6 | 8 | 12 | 5 | 12 | 1 | 2
| 370 | 6 | 6 | 6 | 11 | 7 | 3 | 1 | 5 | 3
| 371 | 20 | 6 | 6 | 11 | 3 | 9 | 11 | 2 | 1
| 372 | 6 | 6 | 6 | 9 | 7 | 5 | 2 | 1 | 3
| 373 | 18 | 6 | 17 | 7 | 5 | 11 | 9 | 3 | 8
| 374 | 18 | 19 | 6 | 7 | 2 | 10 | 9 | 10 | 6
| 375 | 6 | 6 | 17 | 9 | 10 | 5 | 5 | 4 | 8
| 376 | 16 | 6 | 21 | 10 | 3 | 10 | 7 | 6 | 12
| 377 | 16 | 6 | 16 | 9 | 2 | 4 | 7 | 5 | 7
| 378 | 20 | 6 | 6 | 2 | 10 | 4 | 11 | 3 | 4
| 379 | 17 | 6 | 6 | 6 | 4 | 2 | 8 | 4 | 3
| 380 | 19 | 18 | 17 | 9 | 8 | 5 | 10 | 9 | 8
| 381 | 6 | 19 | 6 | 12 | 11 | 1 | 5 | 10 | 2
| 382 | 6 | 6 | 19 | 11 | 7 | 5 | 1 | 3 | 10
| 383 | 6 | 16 | 21 | 1 | 5 | 6 | 4 | 7 | 12
| 384 | 6 | 6 | 18 | 1 | 2 | 3 | 4 | 3 | 9
| 385 | 6 | 6 | 19 | 8 | 12 | 2 | 3 | 1 | 10
| 386 | 18 | 16 | 19 | 7 | 7 | 8 | 9 | 7 | 10
| 387 | 21 | 6 | 20 | 6 | 7 | 9 | 12 | 5 | 11
| 388 | 16 | 18 | 21 | 2 | 4 | 10 | 7 | 9 | 12
| 389 | 6 | 19 | 17 | 6 | 3 | 2 | 4 | 10 | 8
| 390 | 6 | 6 | 6 | 1 | 4 | 8 | 3 | 6 | 5
| 391 | 19 | 16 | 20 | 3 | 12 | 6 | 10 | 7 | 11
| 392 | 6 | 19 | 19 | 6 | 1 | 2 | 6 | 10 | 10
| 393 | 17 | 6 | 16 | 7 | 7 | 1 | 8 | 3 | 7
| 394 | 6 | 20 | 6 | 1 | 2 | 2 | 4 | 11 | 6
| 395 | 6 | 21 | 6 | 10 | 7 | 4 | 6 | 12 | 2
| 396 | 21 | 6 | 6 | 8 | 1 | 1 | 12 | 6 | 1
| 397 | 6 | 19 | 6 | 1 | 11 | 1 | 1 | 10 | 6
| 398 | 6 | 20 | 19 | 6 | 6 | 8 | 3 | 11 | 10
| 399 | 21 | 19 | 6 | 8 | 5 | 4 | 12 | 10 | 2
| 400 | 17 | 16 | 17 | 3 | 12 | 1 | 8 | 7 | 8
| 401 | 6 | 6 | 6 | 9 | 3 | 5 | 3 | 5 | 3
| 402 | 20 | 16 | 19 | 4 | 5 | 1 | 11 | 7 | 10
| 403 | 21 | 6 | 6 | 4 | 5 | 5 | 12 | 4 | 5
| 404 | 6 | 6 | 6 | 12 | 1 | 5 | 1 | 3 | 1
| 405 | 6 | 21 | 6 | 9 | 12 | 10 | 4 | 12 | 3
| 406 | 6 | 19 | 6 | 4 | 5 | 1 | 1 | 10 | 2
| 407 | 17 | 6 | 17 | 4 | 1 | 1 | 8 | 2 | 8
| 408 | 6 | 16 | 19 | 11 | 8 | 9 | 2 | 7 | 10
| 409 | 6 | 17 | 20 | 12 | 9 | 11 | 6 | 8 | 11
| 410 | 20 | 17 | 6 | 2 | 4 | 4 | 11 | 8 | 6
| 411 | 6 | 18 | 6 | 7 | 10 | 5 | 1 | 9 | 4
| 412 | 19 | 6 | 18 | 10 | 10 | 5 | 10 | 4 | 9
| 413 | 16 | 6 | 6 | 10 | 3 | 11 | 7 | 2 | 2
| 414 | 6 | 21 | 18 | 4 | 6 | 8 | 5 | 12 | 9
| 415 | 6 | 6 | 6 | 11 | 3 | 1 | 5 | 4 | 6
| 416 | 6 | 6 | 18 | 5 | 8 | 8 | 5 | 6 | 9
| 417 | 16 | 6 | 18 | 1 | 7 | 3 | 7 | 5 | 9
| 418 | 6 | 21 | 21 | 4 | 7 | 5 | 6 | 12 | 12
| 419 | 6 | 18 | 6 | 7 | 6 | 6 | 4 | 9 | 3
| 420 | 6 | 6 | 21 | 3 | 2 | 2 | 1 | 2 | 12
| 421 | 16 | 6 | 6 | 11 | 11 | 7 | 7 | 5 | 1
| 422 | 6 | 6 | 6 | 10 | 1 | 9 | 6 | 4 | 4
| 423 | 18 | 16 | 6 | 3 | 2 | 7 | 9 | 7 | 5
| 424 | 6 | 6 | 6 | 10 | 11 | 4 | 4 | 4 | 3
| 425 | 20 | 6 | 19 | 3 | 9 | 3 | 11 | 5 | 10
| 426 | 6 | 21 | 21 | 4 | 9 | 5 | 3 | 12 | 12
| 427 | 18 | 6 | 18 | 1 | 10 | 8 | 9 | 2 | 9
| 428 | 6 | 17 | 20 | 3 | 4 | 4 | 1 | 8 | 11
| 429 | 6 | 19 | 6 | 12 | 10 | 2 | 6 | 10 | 4
| 430 | 16 | 6 | 21 | 8 | 6 | 11 | 7 | 2 | 12
| 431 | 17 | 16 | 19 | 10 | 7 | 10 | 8 | 7 | 10
| 432 | 20 | 17 | 6 | 7 | 8 | 12 | 11 | 8 | 3
| 433 | 18 | 6 | 20 | 12 | 12 | 6 | 9 | 1 | 11
| 434 | 17 | 6 | 6 | 12 | 3 | 3 | 8 | 3 | 2
| 435 | 6 | 17 | 18 | 4 | 2 | 10 | 1 | 8 | 9
| 436 | 17 | 17 | 6 | 9 | 6 | 4 | 8 | 8 | 2
| 437 | 20 | 6 | 17 | 9 | 5 | 3 | 11 | 5 | 8
| 438 | 19 | 17 | 16 | 2 | 1 | 6 | 10 | 8 | 7
| 439 | 6 | 16 | 6 | 6 | 12 | 7 | 2 | 7 | 2
| 440 | 20 | 6 | 21 | 4 | 9 | 8 | 11 | 2 | 12
| 441 | 18 | 6 | 21 | 10 | 6 | 3 | 9 | 4 | 12
| 442 | 20 | 20 | 18 | 5 | 6 | 3 | 11 | 11 | 9
| 443 | 6 | 6 | 17 | 2 | 7 | 7 | 5 | 3 | 8
| 444 | 18 | 6 | 18 | 2 | 6 | 6 | 9 | 3 | 9
| 445 | 6 | 6 | 19 | 10 | 1 | 12 | 5 | 1 | 10
| 446 | 20 | 6 | 18 | 11 | 7 | 5 | 11 | 1 | 9
| 447 | 18 | 17 | 6 | 11 | 2 | 11 | 9 | 8 | 4
| 448 | 17 | 16 | 6 | 10 | 7 | 10 | 8 | 7 | 1
| 449 | 6 | 6 | 6 | 3 | 5 | 5 | 2 | 1 | 5
| 450 | 18 | 17 | 21 | 9 | 10 | 11 | 9 | 8 | 12
| 451 | 6 | 16 | 18 | 2 | 3 | 8 | 1 | 7 | 9
| 452 | 19 | 6 | 6 | 6 | 3 | 5 | 10 | 4 | 3
| 453 | 17 | 6 | 6 | 12 | 8 | 4 | 8 | 2 | 5
| 454 | 18 | 6 | 19 | 5 | 2 | 6 | 9 | 2 | 10
| 455 | 16 | 6 | 20 | 7 | 10 | 4 | 7 | 2 | 11
| 456 | 6 | 6 | 6 | 8 | 2 | 8 | 4 | 1 | 2
| 457 | 21 | 16 | 18 | 12 | 11 | 8 | 12 | 7 | 9
| 458 | 6 | 20 | 21 | 1 | 11 | 1 | 6 | 11 | 12
| 459 | 6 | 6 | 6 | 3 | 3 | 3 | 4 | 5 | 5
| 460 | 18 | 17 | 6 | 11 | 1 | 4 | 9 | 8 | 5
| 461 | 20 | 21 | 21 | 4 | 6 | 7 | 11 | 12 | 12
| 462 | 6 | 18 | 6 | 8 | 5 | 8 | 2 | 9 | 6
| 463 | 19 | 6 | 6 | 3 | 3 | 10 | 10 | 1 | 6
| 464 | 6 | 6 | 19 | 11 | 8 | 8 | 2 | 5 | 10
| 465 | 16 | 21 | 6 | 1 | 1 | 3 | 7 | 12 | 1
| 466 | 6 | 17 | 16 | 5 | 1 | 1 | 4 | 8 | 7
| 467 | 20 | 6 | 16 | 12 | 12 | 8 | 11 | 5 | 7
| 468 | 6 | 6 | 17 | 1 | 3 | 7 | 5 | 2 | 8
| 469 | 6 | 6 | 6 | 7 | 3 | 9 | 1 | 1 | 5
| 470 | 17 | 18 | 6 | 2 | 4 | 10 | 8 | 9 | 2
| 471 | 19 | 17 | 6 | 1 | 7 | 3 | 10 | 8 | 5
| 472 | 6 | 6 | 6 | 4 | 1 | 12 | 4 | 1 | 2
| 473 | 19 | 18 | 6 | 5 | 8 | 11 | 10 | 9 | 6
| 474 | 21 | 6 | 18 | 9 | 6 | 5 | 12 | 2 | 9
| 475 | 20 | 21 | 6 | 5 | 12 | 2 | 11 | 12 | 4
| 476 | 6 | 6 | 6 | 3 | 1 | 4 | 2 | 1 | 3
| 477 | 6 | 20 | 6 | 10 | 12 | 1 | 1 | 11 | 3
| 478 | 20 | 6 | 6 | 7 | 6 | 2 | 11 | 3 | 6
| 479 | 6 | 6 | 20 | 3 | 8 | 6 | 5 | 6 | 11
| 480 | 17 | 19 | 6 | 1 | 10 | 7 | 8 | 10 | 4
| 481 | 17 | 21 | 6 | 8 | 10 | 12 | 8 | 12 | 4
| 482 | 6 | 6 | 6 | 2 | 2 | 8 | 5 | 1 | 5
| 483 | 17 | 6 | 20 | 5 | 11 | 7 | 8 | 1 | 11
| 484 | 6 | 18 | 18 | 2 | 11 | 6 | 6 | 9 | 9
| 485 | 6 | 6 | 6 | 10 | 3 | 7 | 4 | 1 | 1
| 486 | 19 | 19 | 16 | 5 | 5 | 11 | 10 | 10 | 7
| 487 | 16 | 6 | 6 | 5 | 6 | 2 | 7 | 4 | 5
| 488 | 18 | 6 | 6 | 1 | 5 | 6 | 9 | 6 | 2
| 489 | 20 | 16 | 6 | 12 | 7 | 11 | 11 | 7 | 1
| 490 | 6 | 19 | 6 | 9 | 5 | 3 | 5 | 10 | 3
| 491 | 16 | 20 | 20 | 4 | 7 | 10 | 7 | 11 | 11
| 492 | 6 | 17 | 18 | 5 | 4 | 3 | 2 | 8 | 9
| 493 | 6 | 20 | 6 | 2 | 6 | 2 | 3 | 11 | 6
| 494 | 6 | 6 | 17 | 3 | 1 | 2 | 3 | 4 | 8
| 495 | 21 | 6 | 20 | 6 | 10 | 11 | 12 | 3 | 11
| 496 | 16 | 6 | 21 | 7 | 4 | 9 | 7 | 1 | 12
| 497 | 6 | 6 | 16 | 5 | 1 | 12 | 4 | 3 | 7
| 498 | 17 | 16 | 20 | 1 | 12 | 1 | 8 | 7 | 11
| 499 | 16 | 6 | 18 | 2 | 9 | 9 | 7 | 4 | 9
| 500 | 6 | 6 | 6 | 3 | 10 | 7 | 1 | 3 | 1
| 501 | 6 | 6 | 6 | 4 | 3 | 9 | 2 | 4 | 6
| 502 | 16 | 6 | 16 | 12 | 8 | 3 | 7 | 6 | 7
| 503 | 6 | 6 | 16 | 3 | 12 | 8 | 6 | 4 | 7
| 504 | 16 | 6 | 6 | 3 | 9 | 9 | 7 | 2 | 3
| 505 | 17 | 21 | 20 | 6 | 10 | 1 | 8 | 12 | 11
| 506 | 6 | 19 | 6 | 10 | 12 | 2 | 2 | 10 | 4
| 507 | 6 | 20 | 20 | 5 | 1 | 11 | 3 | 11 | 11
| 508 | 6 | 17 | 21 | 11 | 9 | 12 | 1 | 8 | 12
| 509 | 17 | 6 | 17 | 3 | 6 | 5 | 8 | 1 | 8
| 510 | 21 | 19 | 16 | 9 | 10 | 5 | 12 | 10 | 7
| 511 | 6 | 21 | 6 | 6 | 5 | 9 | 1 | 12 | 4
| 512 | 18 | 6 | 21 | 5 | 12 | 5 | 9 | 4 | 12
| 513 | 16 | 6 | 21 | 11 | 12 | 3 | 7 | 4 | 12
| 514 | 6 | 17 | 18 | 10 | 9 | 8 | 1 | 8 | 9
| 515 | 6 | 21 | 6 | 6 | 10 | 1 | 6 | 12 | 6
| 516 | 6 | 20 | 16 | 6 | 2 | 11 | 1 | 11 | 7
| 517 | 18 | 19 | 6 | 4 | 1 | 7 | 9 | 10 | 6
| 518 | 21 | 6 | 6 | 3 | 4 | 10 | 12 | 6 | 1
| 519 | 21 | 6 | 21 | 1 | 9 | 7 | 12 | 6 | 12
| 520 | 19 | 16 | 6 | 8 | 6 | 6 | 10 | 7 | 6
| 521 | 6 | 6 | 6 | 3 | 5 | 2 | 5 | 6 | 6
| 522 | 6 | 6 | 6 | 5 | 1 | 2 | 1 | 6 | 4
| 523 | 16 | 18 | 16 | 9 | 9 | 6 | 7 | 9 | 7
| 524 | 6 | 16 | 6 | 3 | 4 | 5 | 3 | 7 | 1
| 525 | 20 | 6 | 20 | 7 | 6 | 11 | 11 | 5 | 11
| 526 | 19 | 6 | 18 | 2 | 6 | 10 | 10 | 6 | 9
| 527 | 6 | 16 | 16 | 11 | 10 | 6 | 2 | 7 | 7
| 528 | 20 | 6 | 6 | 2 | 9 | 3 | 11 | 3 | 2
| 529 | 6 | 6 | 19 | 10 | 5 | 4 | 4 | 4 | 10
| 530 | 6 | 6 | 6 | 2 | 11 | 1 | 1 | 2 | 4
| 531 | 6 | 17 | 6 | 8 | 2 | 8 | 4 | 8 | 1
| 532 | 16 | 6 | 16 | 3 | 1 | 7 | 7 | 6 | 7
| 533 | 17 | 18 | 6 | 7 | 4 | 12 | 8 | 9 | 6
| 534 | 6 | 6 | 6 | 10 | 2 | 3 | 3 | 4 | 3
| 535 | 6 | 6 | 6 | 6 | 10 | 7 | 3 | 1 | 2
| 536 | 19 | 18 | 20 | 4 | 4 | 3 | 10 | 9 | 11
| 537 | 6 | 6 | 19 | 5 | 3 | 5 | 1 | 4 | 10
| 538 | 6 | 6 | 6 | 10 | 11 | 5 | 5 | 3 | 5
| 539 | 6 | 6 | 20 | 1 | 11 | 9 | 5 | 1 | 11
| 540 | 6 | 6 | 6 | 1 | 11 | 1 | 2 | 5 | 2
| 541 | 18 | 6 | 6 | 4 | 9 | 6 | 9 | 6 | 5
| 542 | 17 | 6 | 6 | 12 | 10 | 3 | 8 | 6 | 4
| 543 | 6 | 6 | 6 | 11 | 4 | 1 | 4 | 5 | 3
| 544 | 6 | 16 | 6 | 2 | 9 | 1 | 3 | 7 | 1
| 545 | 16 | 6 | 17 | 9 | 8 | 9 | 7 | 5 | 8
| 546 | 19 | 6 | 6 | 9 | 7 | 11 | 10 | 3 | 1
| 547 | 6 | 21 | 16 | 10 | 3 | 1 | 5 | 12 | 7
| 548 | 6 | 19 | 6 | 9 | 6 | 2 | 3 | 10 | 1
| 549 | 6 | 16 | 6 | 8 | 6 | 12 | 3 | 7 | 6
| 550 | 6 | 6 | 6 | 1 | 6 | 10 | 2 | 5 | 1
| 551 | 6 | 6 | 6 | 5 | 1 | 4 | 4 | 1 | 5
| 552 | 6 | 20 | 20 | 10 | 1 | 1 | 5 | 11 | 11
| 553 | 16 | 17 | 6 | 9 | 12 | 8 | 7 | 8 | 6
| 554 | 18 | 21 | 6 | 1 | 8 | 12 | 9 | 12 | 5
| 555 | 20 | 6 | 17 | 1 | 9 | 2 | 11 | 3 | 8
| 556 | 6 | 20 | 6 | 6 | 5 | 12 | 1 | 11 | 3
| 557 | 6 | 6 | 6 | 9 | 8 | 12 | 3 | 1 | 3
| 558 | 19 | 18 | 6 | 9 | 3 | 10 | 10 | 9 | 1
| 559 | 21 | 6 | 6 | 7 | 8 | 7 | 12 | 3 | 4
| 560 | 16 | 6 | 6 | 2 | 2 | 9 | 7 | 2 | 1
| 561 | 6 | 18 | 21 | 12 | 12 | 12 | 2 | 9 | 12
| 562 | 19 | 6 | 6 | 5 | 9 | 1 | 10 | 2 | 5
| 563 | 17 | 6 | 17 | 5 | 4 | 4 | 8 | 2 | 8
| 564 | 6 | 6 | 16 | 12 | 1 | 9 | 4 | 4 | 7
| 565 | 6 | 6 | 6 | 7 | 12 | 1 | 6 | 3 | 6
| 566 | 21 | 6 | 6 | 2 | 6 | 8 | 12 | 2 | 5
| 567 | 6 | 20 | 20 | 11 | 9 | 8 | 3 | 11 | 11
| 568 | 6 | 21 | 20 | 12 | 2 | 5 | 1 | 12 | 11
| 569 | 19 | 6 | 6 | 6 | 5 | 8 | 10 | 1 | 2
| 570 | 6 | 19 | 16 | 5 | 11 | 12 | 6 | 10 | 7
| 571 | 16 | 6 | 6 | 7 | 1 | 5 | 7 | 4 | 6
| 572 | 6 | 20 | 6 | 10 | 2 | 11 | 1 | 11 | 4
| 573 | 6 | 18 | 6 | 7 | 10 | 5 | 4 | 9 | 4
| 574 | 18 | 6 | 19 | 8 | 5 | 12 | 9 | 5 | 10
| 575 | 20 | 6 | 6 | 9 | 9 | 9 | 11 | 2 | 6
| 576 | 16 | 6 | 17 | 3 | 3 | 11 | 7 | 3 | 8
| 577 | 6 | 19 | 18 | 1 | 3 | 3 | 3 | 10 | 9
| 578 | 6 | 16 | 17 | 11 | 7 | 3 | 5 | 7 | 8
| 579 | 6 | 6 | 6 | 12 | 6 | 1 | 4 | 5 | 1
| 580 | 6 | 6 | 21 | 7 | 9 | 8 | 4 | 6 | 12
| 581 | 6 | 21 | 19 | 11 | 10 | 2 | 6 | 12 | 10
| 582 | 6 | 17 | 6 | 1 | 11 | 2 | 1 | 8 | 4
| 583 | 18 | 18 | 6 | 2 | 4 | 11 | 9 | 9 | 2
| 584 | 17 | 18 | 19 | 2 | 3 | 4 | 8 | 9 | 10
| 585 | 21 | 18 | 6 | 1 | 11 | 7 | 12 | 9 | 1
| 586 | 6 | 6 | 6 | 11 | 10 | 8 | 2 | 2 | 4
| 587 | 6 | 6 | 6 | 10 | 7 | 11 | 5 | 2 | 3
| 588 | 17 | 6 | 6 | 6 | 4 | 1 | 8 | 3 | 5
| 589 | 6 | 16 | 6 | 6 | 7 | 8 | 3 | 7 | 2
| 590 | 18 | 17 | 6 | 2 | 7 | 4 | 9 | 8 | 5
| 591 | 18 | 19 | 16 | 11 | 8 | 7 | 9 | 10 | 7
| 592 | 6 | 16 | 21 | 4 | 2 | 6 | 6 | 7 | 12
| 593 | 6 | 18 | 17 | 12 | 10 | 6 | 1 | 9 | 8
| 594 | 21 | 6 | 6 | 9 | 7 | 8 | 12 | 5 | 6
| 595 | 6 | 6 | 6 | 5 | 10 | 3 | 5 | 3 | 5
| 596 | 6 | 6 | 18 | 12 | 9 | 6 | 5 | 3 | 9
| 597 | 16 | 6 | 21 | 1 | 8 | 6 | 7 | 6 | 12
| 598 | 6 | 6 | 6 | 4 | 7 | 8 | 4 | 3 | 3
| 599 | 19 | 6 | 21 | 2 | 2 | 8 | 10 | 3 | 12
| 600 | 6 | 16 | 19 | 12 | 12 | 6 | 3 | 7 | 10
| 601 | 21 | 6 | 6 | 12 | 1 | 6 | 12 | 6 | 1
| 602 | 20 | 19 | 6 | 1 | 4 | 6 | 11 | 10 | 2
| 603 | 21 | 21 | 18 | 3 | 4 | 6 | 12 | 12 | 9
| 604 | 17 | 20 | 6 | 2 | 1 | 7 | 8 | 11 | 4
| 605 | 18 | 6 | 6 | 5 | 3 | 10 | 9 | 4 | 6
| 606 | 18 | 6 | 6 | 6 | 1 | 2 | 9 | 5 | 1
| 607 | 6 | 16 | 19 | 8 | 7 | 12 | 6 | 7 | 10
| 608 | 6 | 6 | 20 | 8 | 8 | 3 | 1 | 5 | 11
| 609 | 6 | 6 | 6 | 10 | 5 | 6 | 6 | 3 | 4
| 610 | 6 | 19 | 6 | 12 | 9 | 9 | 2 | 10 | 1
| 611 | 18 | 20 | 6 | 12 | 9 | 5 | 9 | 11 | 3
| 612 | 20 | 6 | 17 | 9 | 1 | 6 | 11 | 6 | 8
| 613 | 18 | 16 | 18 | 1 | 1 | 3 | 9 | 7 | 9
| 614 | 6 | 6 | 20 | 6 | 12 | 3 | 3 | 2 | 11
| 615 | 19 | 6 | 21 | 1 | 2 | 4 | 10 | 5 | 12
| 616 | 6 | 6 | 21 | 1 | 8 | 5 | 5 | 5 | 12
| 617 | 6 | 18 | 6 | 9 | 10 | 7 | 2 | 9 | 2
| 618 | 6 | 20 | 17 | 6 | 5 | 12 | 4 | 11 | 8
| 619 | 19 | 18 | 16 | 4 | 5 | 5 | 10 | 9 | 7
| 620 | 6 | 6 | 6 | 5 | 5 | 9 | 1 | 5 | 2
| 621 | 6 | 21 | 6 | 4 | 4 | 3 | 4 | 12 | 6
| 622 | 19 | 6 | 6 | 7 | 3 | 9 | 10 | 4 | 6
| 623 | 6 | 19 | 6 | 7 | 8 | 5 | 1 | 10 | 5
| 624 | 21 | 6 | 6 | 3 | 11 | 9 | 12 | 1 | 4
| 625 | 21 | 6 | 6 | 7 | 8 | 11 | 12 | 5 | 6
| 626 | 19 | 16 | 18 | 11 | 4 | 8 | 10 | 7 | 9
| 627 | 6 | 6 | 16 | 4 | 12 | 3 | 5 | 3 | 7
| 628 | 6 | 6 | 19 | 1 | 9 | 4 | 2 | 5 | 10
| 629 | 6 | 6 | 6 | 9 | 11 | 9 | 5 | 2 | 2
| 630 | 19 | 6 | 6 | 2 | 9 | 12 | 10 | 5 | 2
| 631 | 19 | 6 | 6 | 1 | 10 | 1 | 10 | 6 | 4
| 632 | 16 | 20 | 19 | 1 | 11 | 8 | 7 | 11 | 10
| 633 | 6 | 19 | 6 | 12 | 1 | 12 | 1 | 10 | 1
| 634 | 6 | 6 | 6 | 3 | 12 | 8 | 2 | 3 | 5
| 635 | 20 | 16 | 16 | 11 | 8 | 2 | 11 | 7 | 7
| 636 | 6 | 6 | 19 | 6 | 7 | 4 | 2 | 5 | 10
| 637 | 6 | 6 | 6 | 4 | 9 | 9 | 6 | 6 | 1
| 638 | 17 | 6 | 6 | 7 | 12 | 1 | 8 | 6 | 2
| 639 | 17 | 6 | 6 | 3 | 1 | 1 | 8 | 4 | 2
| 640 | 20 | 21 | 6 | 6 | 6 | 11 | 11 | 12 | 6
| 641 | 18 | 6 | 6 | 9 | 7 | 3 | 9 | 6 | 5
| 642 | 6 | 6 | 17 | 11 | 6 | 8 | 5 | 2 | 8
| 643 | 16 | 20 | 18 | 9 | 4 | 4 | 7 | 11 | 9
| 644 | 20 | 6 | 17 | 1 | 8 | 6 | 11 | 1 | 8
| 645 | 6 | 6 | 20 | 9 | 9 | 11 | 6 | 5 | 11
| 646 | 6 | 6 | 16 | 5 | 7 | 9 | 2 | 3 | 7
| 647 | 6 | 18 | 17 | 5 | 7 | 3 | 5 | 9 | 8
| 648 | 6 | 18 | 20 | 3 | 8 | 2 | 5 | 9 | 11
| 649 | 6 | 6 | 19 | 10 | 2 | 5 | 5 | 6 | 10
| 650 | 16 | 6 | 6 | 1 | 10 | 8 | 7 | 2 | 3
| 651 | 6 | 6 | 17 | 11 | 8 | 6 | 5 | 3 | 8
| 652 | 17 | 6 | 6 | 1 | 4 | 6 | 8 | 4 | 6
| 653 | 6 | 6 | 16 | 4 | 12 | 7 | 5 | 5 | 7
| 654 | 16 | 6 | 19 | 12 | 2 | 6 | 7 | 4 | 10
| 655 | 19 | 6 | 6 | 5 | 6 | 9 | 10 | 4 | 6
| 656 | 6 | 6 | 6 | 4 | 8 | 1 | 6 | 5 | 2
| 657 | 21 | 6 | 6 | 1 | 11 | 9 | 12 | 6 | 4
| 658 | 6 | 17 | 6 | 4 | 8 | 11 | 2 | 8 | 2
| 659 | 6 | 6 | 6 | 10 | 12 | 6 | 1 | 3 | 6
| 660 | 21 | 18 | 6 | 1 | 5 | 8 | 12 | 9 | 6
| 661 | 6 | 6 | 6 | 8 | 12 | 11 | 6 | 3 | 5
| 662 | 6 | 6 | 6 | 12 | 1 | 10 | 5 | 5 | 1
| 663 | 16 | 18 | 6 | 1 | 9 | 4 | 7 | 9 | 5
| 664 | 6 | 20 | 18 | 4 | 5 | 8 | 1 | 11 | 9
| 665 | 6 | 6 | 16 | 4 | 7 | 6 | 6 | 3 | 7
| 666 | 18 | 18 | 6 | 12 | 7 | 12 | 9 | 9 | 2
| 667 | 18 | 16 | 6 | 6 | 9 | 5 | 9 | 7 | 3
| 668 | 19 | 6 | 21 | 7 | 7 | 4 | 10 | 2 | 12
| 669 | 6 | 17 | 18 | 12 | 11 | 11 | 5 | 8 | 9
| 670 | 6 | 6 | 20 | 8 | 5 | 9 | 2 | 4 | 11
| 671 | 6 | 19 | 6 | 3 | 12 | 10 | 6 | 10 | 6
| 672 | 19 | 6 | 18 | 2 | 1 | 3 | 10 | 6 | 9
| 673 | 6 | 17 | 16 | 1 | 3 | 5 | 2 | 8 | 7
| 674 | 6 | 16 | 6 | 3 | 4 | 2 | 1 | 7 | 2
| 675 | 17 | 6 | 6 | 1 | 8 | 6 | 8 | 5 | 5
| 676 | 18 | 6 | 6 | 1 | 5 | 8 | 9 | 4 | 3
| 677 | 6 | 19 | 6 | 3 | 9 | 12 | 6 | 10 | 6
| 678 | 21 | 21 | 19 | 2 | 11 | 1 | 12 | 12 | 10
| 679 | 20 | 18 | 6 | 8 | 6 | 6 | 11 | 9 | 3
| 680 | 6 | 6 | 6 | 9 | 2 | 11 | 5 | 4 | 2
| 681 | 6 | 16 | 16 | 4 | 12 | 1 | 3 | 7 | 7
| 682 | 21 | 20 | 20 | 5 | 11 | 7 | 12 | 11 | 11
| 683 | 21 | 21 | 18 | 8 | 7 | 9 | 12 | 12 | 9
| 684 | 21 | 6 | 20 | 2 | 8 | 10 | 12 | 2 | 11
| 685 | 16 | 21 | 6 | 12 | 6 | 5 | 7 | 12 | 1
| 686 | 6 | 16 | 17 | 8 | 10 | 3 | 5 | 7 | 8
| 687 | 6 | 6 | 6 | 12 | 10 | 6 | 5 | 6 | 4
| 688 | 21 | 19 | 6 | 9 | 10 | 12 | 12 | 10 | 3
| 689 | 6 | 6 | 20 | 10 | 1 | 5 | 1 | 6 | 11
| 690 | 17 | 17 | 17 | 5 | 10 | 8 | 8 | 8 | 8
| 691 | 20 | 17 | 19 | 12 | 4 | 1 | 11 | 8 | 10
| 692 | 18 | 6 | 17 | 12 | 8 | 9 | 9 | 3 | 8
| 693 | 19 | 21 | 6 | 11 | 4 | 3 | 10 | 12 | 3
| 694 | 18 | 17 | 6 | 12 | 2 | 7 | 9 | 8 | 2
| 695 | 6 | 17 | 21 | 12 | 9 | 8 | 2 | 8 | 12
| 696 | 20 | 6 | 6 | 10 | 9 | 12 | 11 | 6 | 4
| 697 | 16 | 20 | 6 | 10 | 1 | 7 | 7 | 11 | 3
| 698 | 17 | 16 | 20 | 8 | 6 | 6 | 8 | 7 | 11
| 699 | 6 | 6 | 6 | 5 | 10 | 3 | 1 | 6 | 4
| 700 | 19 | 16 | 18 | 6 | 8 | 9 | 10 | 7 | 9
| 701 | 6 | 6 | 6 | 6 | 10 | 7 | 1 | 2 | 5
| 702 | 6 | 6 | 19 | 6 | 5 | 7 | 4 | 4 | 10
| 703 | 16 | 6 | 19 | 4 | 8 | 11 | 7 | 5 | 10
| 704 | 6 | 6 | 6 | 2 | 3 | 9 | 6 | 2 | 4
| 705 | 6 | 19 | 6 | 3 | 10 | 12 | 2 | 10 | 6
| 706 | 18 | 6 | 6 | 6 | 5 | 9 | 9 | 5 | 3
| 707 | 6 | 6 | 20 | 2 | 7 | 6 | 6 | 6 | 11
| 708 | 6 | 6 | 6 | 9 | 12 | 7 | 1 | 4 | 6
| 709 | 19 | 20 | 19 | 3 | 4 | 11 | 10 | 11 | 10
| 710 | 20 | 21 | 19 | 2 | 3 | 2 | 11 | 12 | 10
| 711 | 6 | 6 | 6 | 12 | 10 | 4 | 6 | 5 | 3
| 712 | 6 | 6 | 6 | 12 | 11 | 9 | 4 | 3 | 5
| 713 | 19 | 6 | 21 | 11 | 5 | 5 | 10 | 1 | 12
| 714 | 18 | 6 | 6 | 6 | 6 | 1 | 9 | 5 | 5
| 715 | 17 | 6 | 6 | 12 | 7 | 11 | 8 | 2 | 6
| 716 | 19 | 6 | 6 | 3 | 10 | 3 | 10 | 5 | 1
| 717 | 21 | 19 | 6 | 5 | 5 | 4 | 12 | 10 | 1
| 718 | 16 | 17 | 16 | 3 | 10 | 12 | 7 | 8 | 7
| 719 | 20 | 6 | 6 | 10 | 11 | 2 | 11 | 6 | 3
| 720 | 19 | 20 | 16 | 3 | 6 | 7 | 10 | 11 | 7
| 721 | 19 | 6 | 6 | 7 | 4 | 4 | 10 | 6 | 4
| 722 | 6 | 6 | 16 | 7 | 4 | 12 | 4 | 4 | 7
| 723 | 6 | 6 | 6 | 7 | 5 | 8 | 1 | 6 | 1
| 724 | 6 | 21 | 6 | 12 | 8 | 11 | 2 | 12 | 1
| 725 | 20 | 6 | 6 | 7 | 6 | 3 | 11 | 1 | 4
| 726 | 6 | 6 | 6 | 5 | 12 | 2 | 6 | 3 | 6
| 727 | 6 | 6 | 6 | 4 | 10 | 9 | 6 | 4 | 5
| 728 | 21 | 6 | 6 | 8 | 3 | 9 | 12 | 5 | 5
| 729 | 6 | 6 | 19 | 7 | 9 | 9 | 2 | 4 | 10
| 730 | 17 | 6 | 6 | 12 | 8 | 11 | 8 | 3 | 4
| 731 | 18 | 6 | 6 | 12 | 2 | 4 | 9 | 6 | 3
| 732 | 17 | 19 | 6 | 2 | 7 | 6 | 8 | 10 | 3
| 733 | 6 | 6 | 21 | 8 | 11 | 1 | 2 | 1 | 12
| 734 | 6 | 19 | 6 | 2 | 8 | 7 | 4 | 10 | 5
| 735 | 6 | 6 | 20 | 5 | 8 | 10 | 2 | 6 | 11
| 736 | 6 | 18 | 6 | 9 | 6 | 8 | 3 | 9 | 5
| 737 | 6 | 21 | 16 | 12 | 7 | 6 | 4 | 12 | 7
| 738 | 21 | 6 | 21 | 10 | 9 | 4 | 12 | 3 | 12
| 739 | 6 | 6 | 6 | 9 | 8 | 8 | 3 | 6 | 3
| 740 | 6 | 6 | 6 | 5 | 12 | 9 | 5 | 1 | 3
| 741 | 16 | 16 | 6 | 9 | 1 | 4 | 7 | 7 | 5
| 742 | 19 | 6 | 6 | 1 | 1 | 9 | 10 | 2 | 5
| 743 | 6 | 6 | 6 | 12 | 1 | 10 | 6 | 6 | 6
| 744 | 16 | 6 | 6 | 7 | 4 | 5 | 7 | 2 | 5
| 745 | 16 | 6 | 6 | 6 | 7 | 5 | 7 | 3 | 6
| 746 | 6 | 6 | 6 | 11 | 1 | 6 | 5 | 6 | 1
| 747 | 6 | 6 | 6 | 9 | 5 | 11 | 4 | 3 | 6
| 748 | 18 | 6 | 6 | 10 | 7 | 10 | 9 | 4 | 3
| 749 | 6 | 17 | 16 | 1 | 7 | 1 | 4 | 8 | 7
| 750 | 6 | 6 | 6 | 9 | 10 | 10 | 3 | 4 | 5
| 751 | 6 | 6 | 6 | 7 | 1 | 8 | 5 | 6 | 6
| 752 | 6 | 6 | 20 | 6 | 12 | 9 | 6 | 4 | 11
| 753 | 21 | 18 | 16 | 8 | 4 | 6 | 12 | 9 | 7
| 754 | 6 | 21 | 17 | 6 | 6 | 4 | 6 | 12 | 8
| 755 | 6 | 17 | 18 | 8 | 6 | 1 | 1 | 8 | 9
| 756 | 17 | 6 | 6 | 11 | 4 | 2 | 8 | 4 | 5
| 757 | 20 | 17 | 6 | 9 | 8 | 4 | 11 | 8 | 6
| 758 | 6 | 21 | 6 | 11 | 3 | 8 | 2 | 12 | 1
| 759 | 6 | 6 | 6 | 6 | 9 | 11 | 4 | 5 | 2
| 760 | 17 | 19 | 6 | 2 | 4 | 7 | 8 | 10 | 4
| 761 | 6 | 6 | 6 | 5 | 4 | 7 | 5 | 2 | 4
| 762 | 17 | 6 | 6 | 3 | 7 | 2 | 8 | 2 | 6
| 763 | 6 | 6 | 19 | 2 | 5 | 7 | 5 | 2 | 10
| 764 | 17 | 17 | 19 | 8 | 3 | 11 | 8 | 8 | 10
| 765 | 6 | 21 | 19 | 5 | 11 | 4 | 6 | 12 | 10
| 766 | 6 | 6 | 6 | 3 | 4 | 10 | 4 | 2 | 4
| 767 | 21 | 21 | 19 | 11 | 1 | 9 | 12 | 12 | 10
| 768 | 6 | 19 | 19 | 2 | 12 | 2 | 2 | 10 | 10
| 769 | 6 | 6 | 6 | 4 | 9 | 5 | 5 | 4 | 2
| 770 | 6 | 16 | 19 | 3 | 12 | 11 | 2 | 7 | 10
| 771 | 6 | 18 | 19 | 9 | 4 | 4 | 1 | 9 | 10
| 772 | 6 | 6 | 18 | 4 | 4 | 4 | 4 | 6 | 9
| 773 | 18 | 6 | 6 | 5 | 6 | 8 | 9 | 4 | 4
| 774 | 6 | 6 | 20 | 9 | 5 | 5 | 3 | 2 | 11
| 775 | 17 | 6 | 21 | 5 | 1 | 4 | 8 | 5 | 12
| 776 | 6 | 18 | 6 | 10 | 1 | 5 | 1 | 9 | 6
| 777 | 19 | 20 | 18 | 6 | 6 | 6 | 10 | 11 | 9
| 778 | 16 | 6 | 6 | 2 | 10 | 3 | 7 | 3 | 4
| 779 | 21 | 6 | 20 | 9 | 10 | 8 | 12 | 4 | 11
| 780 | 6 | 18 | 19 | 4 | 5 | 1 | 2 | 9 | 10
| 781 | 16 | 6 | 6 | 12 | 9 | 4 | 7 | 5 | 3
| 782 | 6 | 6 | 6 | 5 | 1 | 5 | 6 | 6 | 3
| 783 | 18 | 6 | 17 | 12 | 11 | 11 | 9 | 1 | 8
| 784 | 19 | 17 | 6 | 2 | 11 | 9 | 10 | 8 | 2
| 785 | 19 | 6 | 19 | 5 | 2 | 5 | 10 | 4 | 10
| 786 | 16 | 6 | 21 | 11 | 7 | 5 | 7 | 4 | 12
| 787 | 6 | 17 | 6 | 8 | 4 | 5 | 6 | 8 | 5
| 788 | 20 | 6 | 6 | 12 | 1 | 4 | 11 | 3 | 6
| 789 | 21 | 18 | 6 | 3 | 2 | 9 | 12 | 9 | 6
| 790 | 19 | 20 | 16 | 7 | 4 | 9 | 10 | 11 | 7
| 791 | 16 | 6 | 19 | 6 | 8 | 11 | 7 | 6 | 10
| 792 | 17 | 19 | 6 | 3 | 4 | 7 | 8 | 10 | 6
| 793 | 16 | 16 | 20 | 8 | 8 | 3 | 7 | 7 | 11
| 794 | 17 | 19 | 6 | 1 | 1 | 11 | 8 | 10 | 2
| 795 | 20 | 6 | 6 | 7 | 9 | 8 | 11 | 6 | 5
| 796 | 16 | 21 | 6 | 7 | 3 | 11 | 7 | 12 | 6
| 797 | 19 | 6 | 6 | 5 | 2 | 1 | 10 | 4 | 6
| 798 | 6 | 6 | 6 | 1 | 4 | 5 | 1 | 5 | 2
| 799 | 16 | 6 | 6 | 1 | 2 | 2 | 7 | 6 | 1
| 800 | 6 | 18 | 17 | 8 | 4 | 3 | 4 | 9 | 8
| 801 | 18 | 18 | 20 | 12 | 3 | 4 | 9 | 9 | 11
| 802 | 16 | 19 | 6 | 3 | 3 | 12 | 7 | 10 | 1
| 803 | 16 | 6 | 6 | 7 | 1 | 6 | 7 | 6 | 2
| 804 | 6 | 6 | 6 | 5 | 1 | 3 | 3 | 1 | 3
| 805 | 21 | 17 | 6 | 7 | 1 | 9 | 12 | 8 | 6
| 806 | 20 | 21 | 6 | 7 | 1 | 8 | 11 | 12 | 3
| 807 | 6 | 19 | 6 | 2 | 6 | 12 | 4 | 10 | 4
| 808 | 20 | 21 | 21 | 2 | 6 | 6 | 11 | 12 | 12
| 809 | 6 | 19 | 16 | 7 | 6 | 9 | 2 | 10 | 7
| 810 | 6 | 6 | 21 | 11 | 3 | 11 | 2 | 6 | 12
| 811 | 18 | 16 | 6 | 2 | 7 | 12 | 9 | 7 | 3
| 812 | 21 | 6 | 6 | 1 | 6 | 8 | 12 | 4 | 4
| 813 | 6 | 18 | 6 | 1 | 2 | 9 | 6 | 9 | 6
| 814 | 6 | 19 | 6 | 1 | 2 | 12 | 5 | 10 | 5
| 815 | 6 | 6 | 21 | 5 | 12 | 1 | 6 | 4 | 12
| 816 | 6 | 19 | 6 | 11 | 7 | 5 | 5 | 10 | 4
| 817 | 20 | 17 | 6 | 9 | 12 | 11 | 11 | 8 | 6
| 818 | 19 | 21 | 16 | 8 | 11 | 2 | 10 | 12 | 7
| 819 | 6 | 21 | 6 | 8 | 4 | 9 | 6 | 12 | 2
| 820 | 19 | 16 | 20 | 12 | 1 | 9 | 10 | 7 | 11
| 821 | 6 | 19 | 6 | 5 | 8 | 2 | 2 | 10 | 6
| 822 | 6 | 6 | 19 | 11 | 10 | 8 | 3 | 5 | 10
| 823 | 19 | 6 | 21 | 10 | 3 | 11 | 10 | 4 | 12
| 824 | 6 | 6 | 20 | 3 | 11 | 5 | 5 | 5 | 11
| 825 | 6 | 21 | 6 | 6 | 2 | 5 | 1 | 12 | 5
| 826 | 6 | 6 | 6 | 11 | 2 | 9 | 2 | 5 | 5
| 827 | 16 | 19 | 18 | 1 | 12 | 12 | 7 | 10 | 9
| 828 | 21 | 20 | 17 | 1 | 8 | 11 | 12 | 11 | 8
| 829 | 6 | 18 | 6 | 1 | 1 | 5 | 2 | 9 | 5
| 830 | 6 | 6 | 6 | 7 | 10 | 2 | 1 | 4 | 1
| 831 | 6 | 6 | 19 | 10 | 8 | 6 | 5 | 3 | 10
| 832 | 6 | 6 | 18 | 12 | 1 | 9 | 6 | 2 | 9
| 833 | 17 | 6 | 6 | 1 | 9 | 5 | 8 | 4 | 5
| 834 | 20 | 16 | 6 | 1 | 1 | 1 | 11 | 7 | 6
| 835 | 6 | 21 | 17 | 4 | 12 | 1 | 1 | 12 | 8
| 836 | 6 | 6 | 6 | 3 | 9 | 5 | 3 | 5 | 2
| 837 | 6 | 6 | 6 | 3 | 7 | 3 | 2 | 6 | 6
| 838 | 16 | 6 | 18 | 5 | 2 | 4 | 7 | 2 | 9
| 839 | 17 | 20 | 16 | 8 | 11 | 2 | 8 | 11 | 7
| 840 | 16 | 18 | 17 | 12 | 1 | 4 | 7 | 9 | 8
| 841 | 17 | 20 | 6 | 8 | 4 | 2 | 8 | 11 | 5
| 842 | 6 | 6 | 6 | 12 | 5 | 3 | 5 | 5 | 3
| 843 | 6 | 6 | 6 | 9 | 8 | 10 | 3 | 4 | 1
| 844 | 6 | 21 | 6 | 5 | 9 | 3 | 2 | 12 | 1
| 845 | 6 | 20 | 6 | 10 | 11 | 11 | 3 | 11 | 4
| 846 | 21 | 18 | 16 | 4 | 1 | 1 | 12 | 9 | 7
| 847 | 18 | 6 | 6 | 11 | 7 | 4 | 9 | 4 | 1
| 848 | 21 | 17 | 16 | 6 | 7 | 9 | 12 | 8 | 7
| 849 | 6 | 6 | 6 | 7 | 1 | 8 | 1 | 1 | 5
| 850 | 6 | 6 | 6 | 8 | 10 | 12 | 5 | 6 | 6
| 851 | 6 | 6 | 21 | 1 | 7 | 11 | 6 | 6 | 12
| 852 | 18 | 17 | 21 | 2 | 5 | 1 | 9 | 8 | 12
| 853 | 6 | 17 | 6 | 4 | 4 | 10 | 5 | 8 | 4
| 854 | 21 | 18 | 6 | 2 | 2 | 7 | 12 | 9 | 3
| 855 | 21 | 6 | 6 | 8 | 4 | 10 | 12 | 5 | 6
| 856 | 6 | 21 | 20 | 3 | 11 | 8 | 5 | 12 | 11
| 857 | 6 | 16 | 20 | 12 | 4 | 12 | 3 | 7 | 11
| 858 | 6 | 21 | 6 | 5 | 9 | 8 | 3 | 12 | 1
| 859 | 19 | 6 | 6 | 3 | 7 | 9 | 10 | 2 | 3
| 860 | 6 | 18 | 6 | 6 | 11 | 11 | 3 | 9 | 3
| 861 | 6 | 20 | 18 | 1 | 3 | 2 | 5 | 11 | 9
| 862 | 18 | 21 | 6 | 11 | 6 | 11 | 9 | 12 | 3
| 863 | 17 | 16 | 17 | 4 | 5 | 9 | 8 | 7 | 8
| 864 | 6 | 17 | 6 | 1 | 10 | 9 | 6 | 8 | 2
| 865 | 6 | 21 | 6 | 8 | 2 | 9 | 3 | 12 | 4
| 866 | 6 | 17 | 21 | 5 | 8 | 12 | 5 | 8 | 12
| 867 | 21 | 6 | 6 | 12 | 6 | 9 | 12 | 3 | 6
| 868 | 6 | 6 | 6 | 1 | 11 | 7 | 1 | 4 | 3
| 869 | 6 | 6 | 20 | 7 | 3 | 8 | 4 | 5 | 11
| 870 | 6 | 6 | 6 | 1 | 5 | 5 | 6 | 4 | 4
| 871 | 17 | 6 | 6 | 8 | 1 | 6 | 8 | 4 | 4
| 872 | 18 | 6 | 16 | 1 | 10 | 8 | 9 | 1 | 7
| 873 | 20 | 21 | 6 | 3 | 10 | 6 | 11 | 12 | 1
| 874 | 6 | 20 | 6 | 2 | 6 | 7 | 2 | 11 | 5
| 875 | 21 | 6 | 6 | 8 | 9 | 9 | 12 | 3 | 1
| 876 | 18 | 21 | 6 | 3 | 12 | 8 | 9 | 12 | 1
| 877 | 18 | 18 | 6 | 9 | 6 | 4 | 9 | 9 | 3
| 878 | 18 | 16 | 17 | 9 | 5 | 2 | 9 | 7 | 8
| 879 | 6 | 6 | 6 | 5 | 12 | 7 | 6 | 3 | 4
| 880 | 18 | 6 | 16 | 9 | 4 | 1 | 9 | 2 | 7
| 881 | 6 | 16 | 20 | 7 | 1 | 10 | 5 | 7 | 11
| 882 | 16 | 20 | 17 | 5 | 5 | 12 | 7 | 11 | 8
| 883 | 6 | 6 | 16 | 1 | 5 | 1 | 3 | 3 | 7
| 884 | 20 | 16 | 16 | 7 | 5 | 3 | 11 | 7 | 7
| 885 | 6 | 19 | 18 | 4 | 11 | 11 | 5 | 10 | 9
| 886 | 6 | 16 | 20 | 12 | 5 | 1 | 4 | 7 | 11
| 887 | 18 | 17 | 6 | 12 | 9 | 5 | 9 | 8 | 5
| 888 | 6 | 6 | 6 | 6 | 11 | 10 | 6 | 3 | 2
| 889 | 21 | 6 | 6 | 10 | 7 | 4 | 12 | 3 | 4
| 890 | 16 | 6 | 19 | 12 | 12 | 9 | 7 | 3 | 10
| 891 | 18 | 21 | 6 | 2 | 12 | 4 | 9 | 12 | 4
| 892 | 6 | 21 | 20 | 6 | 6 | 7 | 4 | 12 | 11
| 893 | 21 | 6 | 6 | 10 | 2 | 5 | 12 | 6 | 4
| 894 | 20 | 6 | 17 | 12 | 1 | 5 | 11 | 5 | 8
| 895 | 16 | 16 | 6 | 8 | 6 | 1 | 7 | 7 | 1
| 896 | 19 | 16 | 19 | 1 | 4 | 2 | 10 | 7 | 10
| 897 | 20 | 6 | 20 | 3 | 4 | 10 | 11 | 2 | 11
| 898 | 6 | 19 | 17 | 6 | 12 | 6 | 2 | 10 | 8
| 899 | 6 | 6 | 20 | 12 | 3 | 8 | 2 | 5 | 11
| 900 | 6 | 21 | 6 | 5 | 9 | 3 | 2 | 12 | 4
| 901 | 17 | 6 | 16 | 4 | 6 | 10 | 8 | 3 | 7
| 902 | 18 | 6 | 20 | 9 | 9 | 6 | 9 | 6 | 11
| 903 | 17 | 6 | 6 | 7 | 5 | 4 | 8 | 1 | 3
| 904 | 6 | 17 | 21 | 5 | 4 | 5 | 5 | 8 | 12
| 905 | 21 | 6 | 6 | 1 | 9 | 6 | 12 | 1 | 2
| 906 | 6 | 20 | 17 | 4 | 4 | 9 | 5 | 11 | 8
| 907 | 6 | 18 | 17 | 3 | 2 | 2 | 2 | 9 | 8
| 908 | 6 | 6 | 21 | 2 | 1 | 9 | 6 | 6 | 12
| 909 | 21 | 18 | 20 | 11 | 10 | 2 | 12 | 9 | 11
| 910 | 16 | 6 | 20 | 3 | 11 | 8 | 7 | 5 | 11
| 911 | 21 | 17 | 19 | 11 | 4 | 7 | 12 | 8 | 10
| 912 | 21 | 17 | 6 | 12 | 8 | 1 | 12 | 8 | 4
| 913 | 21 | 20 | 17 | 3 | 10 | 9 | 12 | 11 | 8
| 914 | 17 | 6 | 21 | 6 | 6 | 4 | 8 | 3 | 12
| 915 | 6 | 20 | 6 | 9 | 4 | 1 | 5 | 11 | 4
| 916 | 6 | 18 | 17 | 1 | 5 | 12 | 5 | 9 | 8
| 917 | 19 | 6 | 18 | 4 | 3 | 8 | 10 | 5 | 9
| 918 | 17 | 6 | 21 | 6 | 12 | 2 | 8 | 4 | 12
| 919 | 17 | 20 | 6 | 1 | 7 | 10 | 8 | 11 | 2
| 920 | 6 | 6 | 21 | 5 | 9 | 7 | 3 | 4 | 12
| 921 | 6 | 20 | 6 | 11 | 11 | 9 | 6 | 11 | 3
| 922 | 16 | 6 | 6 | 6 | 6 | 5 | 7 | 2 | 4
| 923 | 6 | 16 | 19 | 10 | 11 | 12 | 6 | 7 | 10
| 924 | 17 | 18 | 21 | 4 | 6 | 7 | 8 | 9 | 12
| 925 | 6 | 18 | 19 | 9 | 8 | 1 | 2 | 9 | 10
| 926 | 6 | 6 | 16 | 6 | 1 | 2 | 1 | 5 | 7
| 927 | 18 | 18 | 16 | 3 | 3 | 9 | 9 | 9 | 7
| 928 | 19 | 6 | 16 | 3 | 3 | 7 | 10 | 2 | 7
| 929 | 6 | 20 | 17 | 9 | 8 | 6 | 5 | 11 | 8
| 930 | 20 | 6 | 17 | 10 | 10 | 2 | 11 | 2 | 8
| 931 | 20 | 18 | 6 | 11 | 1 | 8 | 11 | 9 | 5
| 932 | 17 | 18 | 6 | 9 | 7 | 6 | 8 | 9 | 1
| 933 | 17 | 6 | 16 | 11 | 12 | 9 | 8 | 3 | 7
| 934 | 6 | 16 | 19 | 8 | 9 | 1 | 1 | 7 | 10
| 935 | 18 | 20 | 6 | 7 | 7 | 3 | 9 | 11 | 2
| 936 | 6 | 6 | 20 | 3 | 12 | 2 | 1 | 6 | 11
| 937 | 20 | 6 | 19 | 2 | 3 | 10 | 11 | 2 | 10
| 938 | 6 | 6 | 21 | 12 | 2 | 1 | 3 | 2 | 12
| 939 | 21 | 16 | 18 | 3 | 10 | 11 | 12 | 7 | 9
| 940 | 6 | 20 | 16 | 11 | 8 | 2 | 2 | 11 | 7
| 941 | 17 | 21 | 19 | 1 | 9 | 7 | 8 | 12 | 10
| 942 | 6 | 6 | 6 | 7 | 1 | 9 | 1 | 1 | 1
| 943 | 20 | 18 | 6 | 4 | 5 | 2 | 11 | 9 | 4
| 944 | 18 | 6 | 6 | 8 | 5 | 4 | 9 | 3 | 3
| 945 | 17 | 6 | 18 | 6 | 1 | 6 | 8 | 5 | 9
| 946 | 6 | 17 | 17 | 11 | 11 | 6 | 4 | 8 | 8
| 947 | 6 | 20 | 6 | 6 | 4 | 3 | 3 | 11 | 2
| 948 | 17 | 20 | 6 | 8 | 1 | 11 | 8 | 11 | 1
| 949 | 21 | 17 | 6 | 6 | 8 | 1 | 12 | 8 | 2
| 950 | 6 | 6 | 6 | 12 | 8 | 10 | 3 | 2 | 3
| 951 | 6 | 16 | 17 | 12 | 10 | 11 | 2 | 7 | 8
| 952 | 6 | 6 | 21 | 7 | 6 | 1 | 5 | 1 | 12
| 953 | 6 | 19 | 6 | 2 | 5 | 1 | 5 | 10 | 4
| 954 | 6 | 17 | 16 | 9 | 9 | 1 | 1 | 8 | 7
| 955 | 6 | 20 | 17 | 7 | 12 | 11 | 5 | 11 | 8
| 956 | 21 | 6 | 20 | 12 | 10 | 10 | 12 | 5 | 11
| 957 | 16 | 20 | 6 | 10 | 8 | 8 | 7 | 11 | 5
| 958 | 20 | 6 | 18 | 12 | 6 | 4 | 11 | 2 | 9
| 959 | 19 | 20 | 6 | 7 | 5 | 8 | 10 | 11 | 5
| 960 | 16 | 6 | 21 | 3 | 3 | 6 | 7 | 2 | 12
| 961 | 6 | 17 | 16 | 6 | 12 | 8 | 3 | 8 | 7
| 962 | 19 | 6 | 16 | 7 | 2 | 11 | 10 | 5 | 7
| 963 | 6 | 21 | 17 | 2 | 3 | 11 | 4 | 12 | 8
| 964 | 6 | 17 | 6 | 6 | 10 | 12 | 6 | 8 | 6
| 965 | 6 | 16 | 6 | 7 | 10 | 4 | 4 | 7 | 1
| 966 | 6 | 21 | 6 | 10 | 7 | 9 | 4 | 12 | 1
| 967 | 17 | 6 | 19 | 5 | 3 | 3 | 8 | 3 | 10
| 968 | 6 | 6 | 20 | 11 | 12 | 5 | 3 | 4 | 11
| 969 | 6 | 21 | 20 | 9 | 4 | 6 | 3 | 12 | 11
| 970 | 17 | 17 | 6 | 11 | 8 | 1 | 8 | 8 | 1
| 971 | 6 | 6 | 6 | 8 | 11 | 11 | 3 | 6 | 3
| 972 | 17 | 6 | 16 | 6 | 12 | 4 | 8 | 6 | 7
| 973 | 21 | 6 | 6 | 8 | 5 | 9 | 12 | 3 | 1
| 974 | 6 | 6 | 6 | 2 | 1 | 12 | 4 | 6 | 1
| 975 | 6 | 6 | 19 | 1 | 7 | 5 | 2 | 1 | 10
| 976 | 20 | 20 | 20 | 4 | 12 | 6 | 11 | 11 | 11
| 977 | 6 | 6 | 6 | 10 | 2 | 12 | 5 | 4 | 1
| 978 | 6 | 17 | 17 | 1 | 10 | 5 | 5 | 8 | 8
| 979 | 6 | 6 | 16 | 10 | 3 | 11 | 3 | 3 | 7
| 980 | 21 | 20 | 6 | 7 | 7 | 7 | 12 | 11 | 5
| 981 | 6 | 21 | 16 | 7 | 10 | 4 | 2 | 12 | 7
| 982 | 6 | 18 | 6 | 3 | 5 | 4 | 2 | 9 | 2
| 983 | 18 | 6 | 20 | 2 | 3 | 12 | 9 | 3 | 11
| 984 | 6 | 17 | 19 | 12 | 6 | 3 | 5 | 8 | 10
| 985 | 6 | 6 | 19 | 12 | 3 | 7 | 4 | 2 | 10
| 986 | 6 | 16 | 21 | 2 | 8 | 11 | 4 | 7 | 12
| 987 | 6 | 6 | 18 | 5 | 1 | 1 | 5 | 2 | 9
| 988 | 6 | 20 | 6 | 8 | 8 | 6 | 2 | 11 | 5
| 989 | 6 | 20 | 19 | 11 | 5 | 6 | 5 | 11 | 10
| 990 | 6 | 16 | 19 | 6 | 5 | 4 | 4 | 7 | 10
| 991 | 6 | 21 | 18 | 7 | 10 | 11 | 2 | 12 | 9
| 992 | 18 | 6 | 21 | 12 | 3 | 8 | 9 | 2 | 12
| 993 | 20 | 6 | 6 | 2 | 11 | 12 | 11 | 4 | 5
| 994 | 6 | 6 | 6 | 4 | 5 | 5 | 5 | 6 | 5
| 995 | 6 | 17 | 19 | 6 | 6 | 6 | 5 | 8 | 10
| 996 | 6 | 19 | 6 | 3 | 10 | 3 | 3 | 10 | 6
| 997 | 6 | 21 | 6 | 3 | 3 | 8 | 5 | 12 | 5
| 998 | 16 | 6 | 20 | 1 | 7 | 6 | 7 | 3 | 11
| 999 | 18 | 6 | 21 | 3 | 4 | 5 | 9 | 6 | 12
| 1000 | 6 | 17 | 6 | 3 | 12 | 11 | 1 | 8 | 3

## Abetment1
|  |  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  |  | 16 weeks | Activities |  |  | 16 | 6 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  |  | 21 weeks |  |  |  | 21 | 6 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
Use Proposal to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 36
2 | 1a-2-8-11-17-23-25-26-28 |  | 45
3 | 12-2-8-11-17-23-25-27-28 |  | 46
4 | 1a-2-8-14-17-20-28 |  | 40
5 | 1a-2-8-14-17-23-25-26-28 |  | 49
6 | 12-2-8-14-17-23-25-27-28 |  | 50
7 | 1a-5-8-11-17-20-28 |  | 39
8 | 1a-5-8-11-17-23-25-26-28 |  | 48
9 | 12-5-8-11-17-23-25-27-28 |  | 49
10 | 1a-5-8-14-17-20-28 |  | 43
11 | 1a-5-8-14-17-23-25-26-28 |  | 52
12 | 12-5-8-14-17-23-25-27-28 |  | 53
13 | 1b-3-9-12-18-23-25-26-28 |  | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40
15 | 1b-3-9-12-18-21-28 |  | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42
18 | 1b-3-9-15-18-23-25-26-28 |  | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46
20 | 1b-3-9-15-18-21-28 |  | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48
23 | 1b-6-9-12-18-23-25-26-28 |  | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45
25 | 1b-6-9-12-18-21-28 |  | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47
28 | 1b-6-9-15-18-23-25-26-28 |  | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51
30 | 1b-6-9-15-18-21-28 |  | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53
33 | 1c-4-10-13-19-24-25-26-28 |  | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38
35 | 1c-4-10-13-19-22-28 |  | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42
38 | 1c-4-10-16-19-22-28 |  | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41
41 | 1c-7-10-13-19-22-28 |  | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45
44 | 1c-7-10-16-19-22-28 |  | 33
53
As the project duration is less than 56 weeks, hence we need not crash the activities
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2a to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 41 |  | 0 | 41 |  | 0 | 41
2 | 1a-2-8-11-17-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50
3 | 12-2-8-11-17-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48
4 | 1a-2-8-14-17-20-28 |  | 45 |  | 0 | 45 |  | 0 | 45
5 | 1a-2-8-14-17-23-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54
6 | 12-2-8-14-17-23-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52
7 | 1a-5-8-11-17-20-28 |  | 44 |  | 0 | 44 |  | 1 | 42
8 | 1a-5-8-11-17-23-25-26-28 |  | 53 |  | 0 | 53 |  | 1 | 51
9 | 12-5-8-11-17-23-25-27-28 |  | 54 |  | 1 | 51 |  | 1 | 49
10 | 1a-5-8-14-17-20-28 |  | 48 |  | 0 | 48 |  | 1 | 46
11 | 1a-5-8-14-17-23-25-26-28 |  | 57 |  | 0 | 57 |  | 1 | 55
12 | 1a-5-8-14-17-23-25-27-28 |  | 58 |  | 1 | 55 |  | 1 | 53
13 | 1b-3-9-12-18-23-25-26-28 |  | 39 |  | 0 | 39 |  | 0 | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40 |  | 1 | 37 |  | 0 | 37
15 | 1b-3-9-12-18-21-28 |  | 32 |  | 0 | 32 |  | 0 | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41 |  | 0 | 41 |  | 0 | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42 |  | 1 | 39 |  | 0 | 39
18 | 1b-3-9-15-18-23-25-26-28 |  | 45 |  | 0 | 45 |  | 0 | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46 |  | 1 | 43 |  | 0 | 43
20 | 1b-3-9-15-18-21-28 |  | 38 |  | 0 | 38 |  | 0 | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47 |  | 0 | 47 |  | 0 | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48 |  | 1 | 45 |  | 0 | 45
23 | 1b-6-9-12-18-23-25-26-28 |  | 44 |  | 0 | 44 |  | 0 | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45 |  | 1 | 42 |  | 0 | 42
25 | 1b-6-9-12-18-21-28 |  | 37 |  | 0 | 37 |  | 0 | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46 |  | 0 | 46 |  | 0 | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47 |  | 1 | 44 |  | 0 | 44
28 | 1b-6-9-15-18-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48
30 | 1b-6-9-15-18-21-28 |  | 43 |  | 0 | 43 |  | 0 | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50
33 | 1c-4-10-13-19-24-25-26-28 |  | 37 |  | 0 | 37 |  | 0 | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38 |  | 1 | 35 |  | 0 | 35
35 | 1c-4-10-13-19-22-28 |  | 26 |  | 0 | 26 |  | 0 | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41 |  | 0 | 41 |  | 0 | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42 |  | 1 | 39 |  | 0 | 39
38 | 1c-4-10-16-19-22-28 |  | 30 |  | 0 | 30 |  | 0 | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40 |  | 0 | 40 |  | 0 | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41 |  | 1 | 38 |  | 0 | 38
41 | 1c-7-10-13-19-22-28 |  | 29 |  | 0 | 29 |  | 0 | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44 |  | 0 | 44 |  | 0 | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45 |  | 1 | 42 |  | 0 | 42
44 | 1c-7-10-16-19-22-28 |  | 33 |  | 0 | 33 |  | 0 | 33
|  |  | 58 |  |  | 57 |  |  | 55
If Abetment 1 is delayed to 21 weeks, we need to crash activity 7 and activity 5, to reach deadline of 56 weeks. Cost duration is 48000

## Abetment 2
|  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  | 16 weeks | Activities |  |  | 6 | 16 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | 21 weeks |  |  |  | 6 | 21 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal1 to reduce critical path |  | Use Proposal 2b to reduce critical path |  | Use Proposal 3to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26 |  | 0 | 26 | 0 | 26 | 0 | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35 |  | 0 | 35 | 0 | 35 | 0 | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36 |  | 1 | 33 | 0 | 33 | 0 | 33
4 | 1a-2-8-14-17-20-28 |  | 30 |  | 0 | 30 | 0 | 30 | 0 | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39 |  | 0 | 39 | 0 | 39 | 0 | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40 |  | 1 | 37 | 0 | 37 | 0 | 37
7 | 1a-5-8-11-17-20-28 |  | 29 |  | 0 | 29 | 0 | 29 | 0 | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38 |  | 0 | 38 | 0 | 38 | 0 | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39 |  | 1 | 36 | 0 | 36 | 0 | 36
10 | 1a-5-8-14-17-20-28 |  | 33 |  | 0 | 33 | 0 | 33 | 0 | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42 |  | 0 | 42 | 0 | 42 | 0 | 42
12 | 12-5-8-14-17-23-25-27-28 |  | 43 |  | 1 | 40 | 0 | 40 | 0 | 40
13 | 1b-3-9-12-18-23-25-26-28 |  | 49 |  | 0 | 49 | 0 | 49 | 1 | 46
14 | 1b-3-9-12-18-23-25-27-28 |  | 50 |  | 1 | 47 | 0 | 47 | 1 | 44
15 | 1b-3-9-12-18-21-28 |  | 42 |  | 0 | 42 | 0 | 42 | 1 | 39
16 | 1b-3-9-12-18-24-25-26-28 |  | 51 |  | 0 | 51 | 0 | 51 | 1 | 48
17 | 1b-3-9-12-18-24-25-27-28 |  | 52 |  | 1 | 49 | 0 | 49 | 1 | 46
18 | 1b-3-9-15-18-23-25-26-28 |  | 55 |  | 0 | 55 | 0 | 55 | 1 | 52
19 | 1b-3-9-15-18-23-25-27-28 |  | 56 |  | 1 | 53 | 0 | 53 | 1 | 50
20 | 1b-3-9-15-18-21-28 |  | 48 |  | 0 | 48 | 0 | 48 | 1 | 45
21 | 1b-3-9-15-18-24-25-26-28 |  | 57 |  | 0 | 57 | 0 | 57 | 1 | 54
22 | 1b-3-9-15-18-24-25-27-28 |  | 58 |  | 1 | 55 | 0 | 55 | 1 | 52
23 | 1b-6-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 | 1 | 51 | 1 | 48
24 | 1b-6-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 | 1 | 49 | 1 | 46
25 | 1b-6-9-12-18-21-28 |  | 47 |  | 0 | 47 | 1 | 44 | 1 | 41
26 | 1b-6-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 | 1 | 53 | 1 | 50
27 | 1b-6-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 | 1 | 51 | 1 | 48
28 | 1b-6-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 | 1 | 57 | 1 | 54
29 | 1b-6-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 | 1 | 55 | 1 | 52
30 | 1b-6-9-15-18-21-28 |  | 53 |  | 0 | 53 | 1 | 50 | 1 | 47
31 | 1b-6-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 | 1 | 59 | 1 | 56
32 | 1b-6-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 | 1 | 57 | 1 | 54
33 | 1c-4-10-13-19-24-25-26-28 |  | 37 |  | 0 | 37 | 0 | 37 | 0 | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38 |  | 1 | 35 | 0 | 35 | 0 | 35
35 | 1c-4-10-13-19-22-28 |  | 26 |  | 0 | 26 | 0 | 26 | 0 | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41 |  | 0 | 41 | 0 | 41 | 0 | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42 |  | 1 | 39 | 0 | 39 | 0 | 39
38 | 1c-4-10-16-19-22-28 |  | 30 |  | 0 | 30 | 0 | 30 | 0 | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40 |  | 0 | 40 | 0 | 40 | 0 | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41 |  | 1 | 38 | 0 | 38 | 0 | 38
41 | 1c-7-10-13-19-22-28 |  | 29 |  | 0 | 29 | 0 | 29 | 0 | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44 |  | 0 | 44 | 0 | 44 | 0 | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45 |  | 1 | 42 | 0 | 42 | 0 | 42
44 | 1c-7-10-16-19-22-28 |  | 33 |  | 0 | 33 | 0 | 33 | 0 | 33
|  |  | 63 |  |  | 62 |  | 59 |  | 56
If abetment 2 is delayed by 10weeks, we need to crash activity 27, activity 6 and activity 18 by 3 weeks to achieve our target and increase our cost by 1248000 (8000+40000+400000*)
[5 empty] | Use Proposal1 to reduce critical path |  | Use Proposal 2b to reduce critical path |  | Use Proposal 3to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26 |  | 0 | 26 | 0 | 26 | 0 | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35 |  | 0 | 35 | 0 | 35 | 0 | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36 |  | 1 | 33 | 0 | 33 | 0 | 33
4 | 1a-2-8-14-17-20-28 |  | 30 |  | 0 | 30 | 0 | 30 | 0 | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39 |  | 0 | 39 | 0 | 39 | 0 | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40 |  | 1 | 37 | 0 | 37 | 0 | 37
7 | 1a-5-8-11-17-20-28 |  | 29 |  | 0 | 29 | 0 | 29 | 0 | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38 |  | 0 | 38 | 0 | 38 | 0 | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39 |  | 1 | 36 | 0 | 36 | 0 | 36
10 | 1a-5-8-14-17-20-28 |  | 33 |  | 0 | 33 | 0 | 33 | 0 | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42 |  | 0 | 42 | 0 | 42 | 0 | 42
12 | 1a-5-8-14-17-23-25-27-28 |  | 43 |  | 1 | 40 | 0 | 40 | 0 | 40
13 | 1b-3-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 | 0 | 54 | 1 | 49
14 | 1b-3-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 | 0 | 52 | 1 | 47
15 | 1b-3-9-12-18-21-28 |  | 47 |  | 0 | 47 | 0 | 47 | 1 | 42
16 | 1b-3-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 | 0 | 56 | 1 | 51
17 | 1b-3-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 | 0 | 54 | 1 | 49
18 | 1b-3-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 | 0 | 60 | 1 | 55
19 | 1b-3-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 | 0 | 58 | 1 | 53
20 | 1b-3-9-15-18-21-28 |  | 53 |  | 0 | 53 | 0 | 53 | 1 | 48
21 | 1b-3-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 | 0 | 62 | 1 | 57
22 | 1b-3-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 | 0 | 60 | 1 | 55
23 | 1b-6-9-12-18-23-25-26-28 |  | 59 |  | 0 | 59 | 1 | 56 | 1 | 51
24 | 1b-6-9-12-18-23-25-27-28 |  | 60 |  | 1 | 57 | 1 | 54 | 1 | 49
25 | 1b-6-9-12-18-21-28 |  | 52 |  | 0 | 52 | 1 | 49 | 1 | 44
26 | 1b-6-9-12-18-24-25-26-28 |  | 61 |  | 0 | 61 | 1 | 58 | 1 | 53
27 | 1b-6-9-12-18-24-25-27-28 |  | 62 |  | 1 | 59 | 1 | 56 | 1 | 51
28 | 1b-6-9-15-18-23-25-26-28 |  | 65 |  | 0 | 65 | 1 | 62 | 1 | 57
29 | 1b-6-9-15-18-23-25-27-28 |  | 66 |  | 1 | 63 | 1 | 60 | 1 | 55
30 | 1b-6-9-15-18-21-28 |  | 58 |  | 0 | 58 | 1 | 55 | 1 | 50
31 | 1b-6-9-15-18-24-25-26-28 |  | 67 |  | 0 | 67 | 1 | 64 | 1 | 59
32 | 1b-6-9-15-18-24-25-27-28 |  | 68 |  | 1 | 65 | 1 | 62 | 1 | 57
33 | 1c-4-10-13-19-24-25-26-28 |  | 37 |  | 0 | 37 | 0 | 37 | 0 | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38 |  | 1 | 35 | 0 | 35 | 0 | 35
35 | 1c-4-10-13-19-22-28 |  | 26 |  | 0 | 26 | 0 | 26 | 0 | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41 |  | 0 | 41 | 0 | 41 | 0 | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42 |  | 1 | 39 | 0 | 39 | 0 | 39
38 | 1c-4-10-16-19-22-28 |  | 30 |  | 0 | 30 | 0 | 30 | 0 | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40 |  | 0 | 40 | 0 | 40 | 0 | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41 |  | 1 | 38 | 0 | 38 | 0 | 38
41 | 1c-7-10-13-19-22-28 |  | 29 |  | 0 | 29 | 0 | 29 | 0 | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44 |  | 0 | 44 | 0 | 44 | 0 | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45 |  | 1 | 42 | 0 | 42 | 0 | 42
44 | 1c-7-10-16-19-22-28 |  | 33 |  | 0 | 33 | 0 | 33 | 0 | 33
|  |  | 68 |  |  | 67 |  | 64 |  | 59
If abetment 2 is delayed by 15weeks, we need to crash activity 27, activity 6 and activity 18 by 5 weeks . We will miss ur target by 3 weeks. Our cost is increase by 2048000(8000+40000+400000*5)

## Abetment 3
| Activity Reduction |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  | 16 weeks | Activities |  |  | 6 | 6 | 16 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | 21 weeks |  |  |  | 6 | 6 | 21 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal to reduce critical path |  | Use Proposal to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36
4 | 1a-2-8-14-17-20-28 |  | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40
7 | 1a-5-8-11-17-20-28 |  | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39
10 | 1a-5-8-14-17-20-28 |  | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42
12 | 12-5-8-14-17-23-25-27-28 |  | 43
13 | 1b-3-9-12-18-23-25-26-28 |  | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40
15 | 1b-3-9-12-18-21-28 |  | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42
18 | 1b-3-9-15-18-23-25-26-28 |  | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46
20 | 1b-3-9-15-18-21-28 |  | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48
23 | 1b-6-9-12-18-23-25-26-28 |  | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45
25 | 1b-6-9-12-18-21-28 |  | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47
28 | 1b-6-9-15-18-23-25-26-28 |  | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51
30 | 1b-6-9-15-18-21-28 |  | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53
33 | 1c-4-10-13-19-24-25-26-28 |  | 47
34 | 1c-4-10-13-19-24-25-27-28 |  | 48
35 | 1c-4-10-13-19-22-28 |  | 36
36 | 1c-4-10-16-19-24-25-26-28 |  | 51
37 | 1c-4-10-16-19-24-25-27-28 |  | 52
38 | 1c-4-10-16-19-22-28 |  | 40
39 | 1c-7-10-13-19-24-25-26-28 |  | 50
40 | 1c-7-10-13-19-24-25-27-28 |  | 51
41 | 1c-7-10-13-19-22-28 |  | 39
42 | 1c-7-10-16-19-24-25-26-28 |  | 54
43 | 1c-7-10-16-19-24-25-27-28 |  | 55
44 | 1c-7-10-16-19-22-28 |  | 43
55
As the project can be completed in less than 56 weeks, we don’t need to crash the project
[5 empty] | Use Proposal 1 to reduce critical path |  | Use Proposal 2c to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26 |  | 0 | 26 | 0 | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35 |  | 0 | 35 | 0 | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36 |  | 1 | 33 | 0 | 33
4 | 1a-2-8-14-17-20-28 |  | 30 |  | 0 | 30 | 0 | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39 |  | 0 | 39 | 0 | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40 |  | 1 | 37 | 0 | 37
7 | 1a-5-8-11-17-20-28 |  | 29 |  | 0 | 29 | 0 | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38 |  | 0 | 38 | 0 | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39 |  | 1 | 36 | 0 | 36
10 | 1a-5-8-14-17-20-28 |  | 33 |  | 0 | 33 | 0 | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42 |  | 0 | 42 | 0 | 42
12 | 1a-5-8-14-17-23-25-27-28 |  | 43 |  | 1 | 40 | 0 | 40
13 | 1b-3-9-12-18-23-25-26-28 |  | 39 |  | 0 | 39 | 0 | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40 |  | 1 | 37 | 0 | 37
15 | 1b-3-9-12-18-21-28 |  | 32 |  | 0 | 32 | 0 | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41 |  | 0 | 41 | 0 | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42 |  | 1 | 39 | 0 | 39
18 | 1b-3-9-15-18-23-25-26-28 |  | 45 |  | 0 | 45 | 0 | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46 |  | 1 | 43 | 0 | 43
20 | 1b-3-9-15-18-21-28 |  | 38 |  | 0 | 38 | 0 | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47 |  | 0 | 47 | 0 | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48 |  | 1 | 45 | 0 | 45
23 | 1b-6-9-12-18-23-25-26-28 |  | 44 |  | 0 | 44 | 0 | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45 |  | 1 | 42 | 0 | 42
25 | 1b-6-9-12-18-21-28 |  | 37 |  | 0 | 37 | 0 | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46 |  | 0 | 46 | 0 | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47 |  | 1 | 44 | 0 | 44
28 | 1b-6-9-15-18-23-25-26-28 |  | 50 |  | 0 | 50 | 0 | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51 |  | 1 | 48 | 0 | 48
30 | 1b-6-9-15-18-21-28 |  | 43 |  | 0 | 43 | 0 | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52 |  | 0 | 52 | 0 | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53 |  | 1 | 50 | 0 | 50
33 | 1c-4-10-13-19-24-25-26-28 |  | 52 |  | 0 | 52 | 1 | 50
34 | 1c-4-10-13-19-24-25-27-28 |  | 53 |  | 1 | 50 | 1 | 48
35 | 1c-4-10-13-19-22-28 |  | 41 |  | 0 | 41 | 1 | 39
36 | 1c-4-10-16-19-24-25-26-28 |  | 56 |  | 0 | 56 | 1 | 54
37 | 1c-4-10-16-19-24-25-27-28 |  | 57 |  | 1 | 54 | 1 | 52
38 | 1c-4-10-16-19-22-28 |  | 45 |  | 0 | 45 | 1 | 43
39 | 1c-7-10-13-19-24-25-26-28 |  | 55 |  | 0 | 55 | 1 | 53
40 | 1c-7-10-13-19-24-25-27-28 |  | 56 |  | 1 | 53 | 1 | 51
41 | 1c-7-10-13-19-22-28 |  | 44 |  | 0 | 44 | 1 | 42
42 | 1c-7-10-16-19-24-25-26-28 |  | 59 |  | 0 | 59 | 1 | 57
43 | 1c-7-10-16-19-24-25-27-28 |  | 60 |  | 1 | 57 | 1 | 55
44 | 1c-7-10-16-19-22-28 |  | 48 |  | 0 | 48 | 1 | 46
|  |  | 60 |  |  | 59 |  | 57
If Abetment 3 is delayed to 21 weeks, we need to crash activity 27 and activity 5, and miss our deadline by 1 week. Cost duration is 48000

## Abetment 1 & 2
|  |  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  |  | 16 weeks | Activities |  |  | 16 | 16 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  |  | 21 weeks |  |  |  | 21 | 21 | 6 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal1 to reduce critical path |  |  | Use Proposal 2bto reduce critical path |  |  | Use Proposal 3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 36 |  | 0 | 36 |  | 0 | 36 |  | 0 | 36
2 | 1a-2-8-11-17-23-25-26-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
3 | 12-2-8-11-17-23-25-27-28 |  | 46 |  | 1 | 43 |  | 0 | 43 |  | 0 | 43
4 | 1a-2-8-14-17-20-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40
5 | 1a-2-8-14-17-23-25-26-28 |  | 49 |  | 0 | 49 |  | 0 | 49 |  | 0 | 49
6 | 12-2-8-14-17-23-25-27-28 |  | 50 |  | 1 | 47 |  | 0 | 47 |  | 0 | 47
7 | 1a-5-8-11-17-20-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39
8 | 1a-5-8-11-17-23-25-26-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
9 | 12-5-8-11-17-23-25-27-28 |  | 49 |  | 1 | 46 |  | 0 | 46 |  | 0 | 46
10 | 1a-5-8-14-17-20-28 |  | 43 |  | 0 | 43 |  | 0 | 43 |  | 0 | 43
11 | 1a-5-8-14-17-23-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52 |  | 0 | 52
12 | 12-5-8-14-17-23-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50 |  | 0 | 50
13 | 1b-3-9-12-18-23-25-26-28 |  | 49 |  | 0 | 49 |  | 1 | 46 |  | 1 | 43
14 | 1b-3-9-12-18-23-25-27-28 |  | 50 |  | 1 | 47 |  | 1 | 44 |  | 1 | 41
15 | 1b-3-9-12-18-21-28 |  | 42 |  | 0 | 42 |  | 1 | 39 |  | 1 | 36
16 | 1b-3-9-12-18-24-25-26-28 |  | 51 |  | 0 | 51 |  | 1 | 48 |  | 1 | 45
17 | 1b-3-9-12-18-24-25-27-28 |  | 52 |  | 1 | 49 |  | 1 | 46 |  | 1 | 43
18 | 1b-3-9-15-18-23-25-26-28 |  | 55 |  | 0 | 55 |  | 1 | 52 |  | 1 | 49
19 | 1b-3-9-15-18-23-25-27-28 |  | 56 |  | 1 | 53 |  | 1 | 50 |  | 1 | 47
20 | 1b-3-9-15-18-21-28 |  | 48 |  | 0 | 48 |  | 1 | 45 |  | 1 | 42
21 | 1b-3-9-15-18-24-25-26-28 |  | 57 |  | 0 | 57 |  | 1 | 54 |  | 1 | 51
22 | 1b-3-9-15-18-24-25-27-28 |  | 58 |  | 1 | 55 |  | 1 | 52 |  | 1 | 49
23 | 1b-6-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 1 | 48
24 | 1b-6-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 1 | 46
25 | 1b-6-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 1 | 41
26 | 1b-6-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 1 | 50
27 | 1b-6-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 1 | 48
28 | 1b-6-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 1 | 54
29 | 1b-6-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 1 | 52
30 | 1b-6-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 1 | 47
31 | 1b-6-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 1 | 56
32 | 1b-6-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 1 | 54
33 | 1c-4-10-13-19-24-25-26-28 |  | 37 |  | 0 | 37 |  | 0 | 37 |  | 0 | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38 |  | 1 | 35 |  | 0 | 35 |  | 0 | 35
35 | 1c-4-10-13-19-22-28 |  | 26 |  | 0 | 26 |  | 0 | 26 |  | 0 | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42 |  | 1 | 39 |  | 0 | 39 |  | 0 | 39
38 | 1c-4-10-16-19-22-28 |  | 30 |  | 0 | 30 |  | 0 | 30 |  | 0 | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41 |  | 1 | 38 |  | 0 | 38 |  | 0 | 38
41 | 1c-7-10-13-19-22-28 |  | 29 |  | 0 | 29 |  | 0 | 29 |  | 0 | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45 |  | 1 | 42 |  | 0 | 42 |  | 0 | 42
44 | 1c-7-10-16-19-22-28 |  | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33
|  |  | 63 |  |  | 62 |  |  | 59 |  |  | 56
If actvity 1 and 2 is delayed by 10 weeks, then we need to reduce activity 27, actvity 6 and activity 18 by 3 weeks. Total duration cost is 1248000(8000+40000+400000*3)
[5 empty] | Use Proposal1 to reduce critical path |  |  | Use Proposal 2bto reduce critical path |  |  | Use Proposal 3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
2 | 1a-2-8-11-17-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50 |  | 0 | 50
3 | 12-2-8-11-17-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48 |  | 0 | 48
4 | 1a-2-8-14-17-20-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
5 | 1a-2-8-14-17-23-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54 |  | 0 | 54
6 | 12-2-8-14-17-23-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52 |  | 0 | 52
7 | 1a-5-8-11-17-20-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
8 | 1a-5-8-11-17-23-25-26-28 |  | 53 |  | 0 | 53 |  | 0 | 53 |  | 0 | 53
9 | 12-5-8-11-17-23-25-27-28 |  | 54 |  | 1 | 51 |  | 0 | 51 |  | 0 | 51
10 | 1a-5-8-14-17-20-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
11 | 1a-5-8-14-17-23-25-26-28 |  | 57 |  | 0 | 57 |  | 0 | 57 |  | 0 | 57
12 | 1a-5-8-14-17-23-25-27-28 |  | 58 |  | 1 | 55 |  | 0 | 55 |  | 0 | 55
13 | 1b-3-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 1 | 46
14 | 1b-3-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 1 | 44
15 | 1b-3-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 1 | 39
16 | 1b-3-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 1 | 48
17 | 1b-3-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 1 | 46
18 | 1b-3-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 1 | 52
19 | 1b-3-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 1 | 50
20 | 1b-3-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 1 | 45
21 | 1b-3-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 1 | 54
22 | 1b-3-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 1 | 52
23 | 1b-6-9-12-18-23-25-26-28 |  | 59 |  | 0 | 59 |  | 1 | 56 |  | 1 | 51
24 | 1b-6-9-12-18-23-25-27-28 |  | 60 |  | 1 | 57 |  | 1 | 54 |  | 1 | 49
25 | 1b-6-9-12-18-21-28 |  | 52 |  | 0 | 52 |  | 1 | 49 |  | 1 | 44
26 | 1b-6-9-12-18-24-25-26-28 |  | 61 |  | 0 | 61 |  | 1 | 58 |  | 1 | 53
27 | 1b-6-9-12-18-24-25-27-28 |  | 62 |  | 1 | 59 |  | 1 | 56 |  | 1 | 51
28 | 1b-6-9-15-18-23-25-26-28 |  | 65 |  | 0 | 65 |  | 1 | 62 |  | 1 | 57
29 | 1b-6-9-15-18-23-25-27-28 |  | 66 |  | 1 | 63 |  | 1 | 60 |  | 1 | 55
30 | 1b-6-9-15-18-21-28 |  | 58 |  | 0 | 58 |  | 1 | 55 |  | 1 | 50
31 | 1b-6-9-15-18-24-25-26-28 |  | 67 |  | 0 | 67 |  | 1 | 64 |  | 1 | 59
32 | 1b-6-9-15-18-24-25-27-28 |  | 68 |  | 1 | 65 |  | 1 | 62 |  | 1 | 57
33 | 1c-4-10-13-19-24-25-26-28 |  | 37 |  | 0 | 37 |  | 0 | 37 |  | 0 | 37
34 | 1c-4-10-13-19-24-25-27-28 |  | 38 |  | 1 | 35 |  | 0 | 35 |  | 0 | 35
35 | 1c-4-10-13-19-22-28 |  | 26 |  | 0 | 26 |  | 0 | 26 |  | 0 | 26
36 | 1c-4-10-16-19-24-25-26-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
37 | 1c-4-10-16-19-24-25-27-28 |  | 42 |  | 1 | 39 |  | 0 | 39 |  | 0 | 39
38 | 1c-4-10-16-19-22-28 |  | 30 |  | 0 | 30 |  | 0 | 30 |  | 0 | 30
39 | 1c-7-10-13-19-24-25-26-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40
40 | 1c-7-10-13-19-24-25-27-28 |  | 41 |  | 1 | 38 |  | 0 | 38 |  | 0 | 38
41 | 1c-7-10-13-19-22-28 |  | 29 |  | 0 | 29 |  | 0 | 29 |  | 0 | 29
42 | 1c-7-10-16-19-24-25-26-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
43 | 1c-7-10-16-19-24-25-27-28 |  | 45 |  | 1 | 42 |  | 0 | 42 |  | 0 | 42
44 | 1c-7-10-16-19-22-28 |  | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33
|  |  | 68 |  |  | 67 |  |  | 64 |  |  | 59
If abetment 1 & 2 is delayed by 15weeks, we need to crash activity 27, activity 6 and activity 18 by 5 weeks . We will miss ur target by 3 weeks. Our cost is increase by 2048000(8000+40000+400000*5). WE can crash activity 5 but it will not be improvement in our process

## Abetment 1 & 3
|  |  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  |  | 16 weeks | Activities |  |  | 16 | 6 | 16 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  |  | 21 weeks |  |  |  | 21 | 6 | 21 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal to reduce critical path |  |  | Use Proposal to reduce critical path |  |  | Use Proposal to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 36
2 | 1a-2-8-11-17-23-25-26-28 |  | 45
3 | 12-2-8-11-17-23-25-27-28 |  | 46
4 | 1a-2-8-14-17-20-28 |  | 40
5 | 1a-2-8-14-17-23-25-26-28 |  | 49
6 | 12-2-8-14-17-23-25-27-28 |  | 50
7 | 1a-5-8-11-17-20-28 |  | 39
8 | 1a-5-8-11-17-23-25-26-28 |  | 48
9 | 12-5-8-11-17-23-25-27-28 |  | 49
10 | 1a-5-8-14-17-20-28 |  | 43
11 | 1a-5-8-14-17-23-25-26-28 |  | 52
12 | 12-5-8-14-17-23-25-27-28 |  | 53
13 | 1b-3-9-12-18-23-25-26-28 |  | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40
15 | 1b-3-9-12-18-21-28 |  | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42
18 | 1b-3-9-15-18-23-25-26-28 |  | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46
20 | 1b-3-9-15-18-21-28 |  | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48
23 | 1b-6-9-12-18-23-25-26-28 |  | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45
25 | 1b-6-9-12-18-21-28 |  | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47
28 | 1b-6-9-15-18-23-25-26-28 |  | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51
30 | 1b-6-9-15-18-21-28 |  | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53
33 | 1c-4-10-13-19-24-25-26-28 |  | 47
34 | 1c-4-10-13-19-24-25-27-28 |  | 48
35 | 1c-4-10-13-19-22-28 |  | 36
36 | 1c-4-10-16-19-24-25-26-28 |  | 51
37 | 1c-4-10-16-19-24-25-27-28 |  | 52
38 | 1c-4-10-16-19-22-28 |  | 40
39 | 1c-7-10-13-19-24-25-26-28 |  | 50
40 | 1c-7-10-13-19-24-25-27-28 |  | 51
41 | 1c-7-10-13-19-22-28 |  | 39
42 | 1c-7-10-16-19-24-25-26-28 |  | 54
43 | 1c-7-10-16-19-24-25-27-28 |  | 55
44 | 1c-7-10-16-19-22-28 |  | 43
55
As the project duration is less than 56 weeks, hence we need not crash the activities
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2a to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path'
1 | 1a-2-8-11-17-20-28 |  | 41 |  | 0 | 41 |  | 0 | 41
2 | 1a-2-8-11-17-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50
3 | 12-2-8-11-17-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48
4 | 1a-2-8-14-17-20-28 |  | 45 |  | 0 | 45 |  | 0 | 45
5 | 1a-2-8-14-17-23-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54
6 | 12-2-8-14-17-23-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52
7 | 1a-5-8-11-17-20-28 |  | 44 |  | 0 | 44 |  | 0 | 44
8 | 1a-5-8-11-17-23-25-26-28 |  | 53 |  | 0 | 53 |  | 0 | 53
9 | 12-5-8-11-17-23-25-27-28 |  | 54 |  | 1 | 51 |  | 0 | 51
10 | 1a-5-8-14-17-20-28 |  | 48 |  | 0 | 48 |  | 0 | 48
11 | 1a-5-8-14-17-23-25-26-28 |  | 57 |  | 0 | 57 |  | 0 | 57
12 | 1a-5-8-14-17-23-25-27-28 |  | 58 |  | 1 | 55 |  | 0 | 55
13 | 1b-3-9-12-18-23-25-26-28 |  | 39 |  | 0 | 39 |  | 0 | 39
14 | 1b-3-9-12-18-23-25-27-28 |  | 40 |  | 1 | 37 |  | 0 | 37
15 | 1b-3-9-12-18-21-28 |  | 32 |  | 0 | 32 |  | 0 | 32
16 | 1b-3-9-12-18-24-25-26-28 |  | 41 |  | 0 | 41 |  | 0 | 41
17 | 1b-3-9-12-18-24-25-27-28 |  | 42 |  | 1 | 39 |  | 0 | 39
18 | 1b-3-9-15-18-23-25-26-28 |  | 45 |  | 0 | 45 |  | 0 | 45
19 | 1b-3-9-15-18-23-25-27-28 |  | 46 |  | 1 | 43 |  | 0 | 43
20 | 1b-3-9-15-18-21-28 |  | 38 |  | 0 | 38 |  | 0 | 38
21 | 1b-3-9-15-18-24-25-26-28 |  | 47 |  | 0 | 47 |  | 0 | 47
22 | 1b-3-9-15-18-24-25-27-28 |  | 48 |  | 1 | 45 |  | 0 | 45
23 | 1b-6-9-12-18-23-25-26-28 |  | 44 |  | 0 | 44 |  | 0 | 44
24 | 1b-6-9-12-18-23-25-27-28 |  | 45 |  | 1 | 42 |  | 0 | 42
25 | 1b-6-9-12-18-21-28 |  | 37 |  | 0 | 37 |  | 0 | 37
26 | 1b-6-9-12-18-24-25-26-28 |  | 46 |  | 0 | 46 |  | 0 | 46
27 | 1b-6-9-12-18-24-25-27-28 |  | 47 |  | 1 | 44 |  | 0 | 44
28 | 1b-6-9-15-18-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50
29 | 1b-6-9-15-18-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48
30 | 1b-6-9-15-18-21-28 |  | 43 |  | 0 | 43 |  | 0 | 43
31 | 1b-6-9-15-18-24-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52
32 | 1b-6-9-15-18-24-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50
33 | 1c-4-10-13-19-24-25-26-28 |  | 52 |  | 0 | 52 |  | 1 | 50
34 | 1c-4-10-13-19-24-25-27-28 |  | 53 |  | 1 | 50 |  | 1 | 48
35 | 1c-4-10-13-19-22-28 |  | 41 |  | 0 | 41 |  | 1 | 39
36 | 1c-4-10-16-19-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 54
37 | 1c-4-10-16-19-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 52
38 | 1c-4-10-16-19-22-28 |  | 45 |  | 0 | 45 |  | 1 | 43
39 | 1c-7-10-13-19-24-25-26-28 |  | 55 |  | 0 | 55 |  | 1 | 53
40 | 1c-7-10-13-19-24-25-27-28 |  | 56 |  | 1 | 53 |  | 1 | 51
41 | 1c-7-10-13-19-22-28 |  | 44 |  | 0 | 44 |  | 1 | 42
42 | 1c-7-10-16-19-24-25-26-28 |  | 59 |  | 0 | 59 |  | 1 | 57
43 | 1c-7-10-16-19-24-25-27-28 |  | 60 |  | 1 | 57 |  | 1 | 55
44 | 1c-7-10-16-19-22-28 |  | 48 |  | 0 | 48 |  | 1 | 46
|  |  | 60 |  |  | 59 |  |  | 57
If Abetment 1 and 3 is delayed to 21 weeks, we need to crash activity 7 and activity 5, to reach deadline of 56 weeks. Cost duration is 48000. We may crash activity 5 but we will still not be able to meet our deadline

## Abetment 2 & 3
|  |  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  |  | 16 weeks | Activities |  |  | 6 | 16 | 16 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  |  | 21 weeks |  |  |  | 6 | 21 | 21 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2b to reduce critical path |  |  | Use Proposal 2c to reduce critical path |  |  | Use Proposal3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26 |  | 0 | 26 |  | 0 | 26 |  | 0 | 26 |  | 0 | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35 |  | 0 | 35 |  | 0 | 35 |  | 0 | 35 |  | 0 | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36 |  | 1 | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33
4 | 1a-2-8-14-17-20-28 |  | 30 |  | 0 | 30 |  | 0 | 30 |  | 0 | 30 |  | 0 | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40 |  | 1 | 37 |  | 0 | 37 |  | 0 | 37 |  | 0 | 37
7 | 1a-5-8-11-17-20-28 |  | 29 |  | 0 | 29 |  | 0 | 29 |  | 0 | 29 |  | 0 | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38 |  | 0 | 38 |  | 0 | 38 |  | 0 | 38 |  | 0 | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39 |  | 1 | 36 |  | 0 | 36 |  | 0 | 36 |  | 0 | 36
10 | 1a-5-8-14-17-20-28 |  | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42 |  | 0 | 42 |  | 0 | 42 |  | 0 | 42 |  | 0 | 42
12 | 12-5-8-14-17-23-25-27-28 |  | 43 |  | 1 | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40
13 | 1b-3-9-12-18-23-25-26-28 |  | 49 |  | 0 | 49 |  | 1 | 46 |  | 0 | 46 |  | 1 | 43
14 | 1b-3-9-12-18-23-25-27-28 |  | 50 |  | 1 | 47 |  | 1 | 44 |  | 0 | 44 |  | 1 | 41
15 | 1b-3-9-12-18-21-28 |  | 42 |  | 0 | 42 |  | 1 | 39 |  | 0 | 39 |  | 1 | 36
16 | 1b-3-9-12-18-24-25-26-28 |  | 51 |  | 0 | 51 |  | 1 | 48 |  | 0 | 48 |  | 1 | 45
17 | 1b-3-9-12-18-24-25-27-28 |  | 52 |  | 1 | 49 |  | 1 | 46 |  | 0 | 46 |  | 1 | 43
18 | 1b-3-9-15-18-23-25-26-28 |  | 55 |  | 0 | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 49
19 | 1b-3-9-15-18-23-25-27-28 |  | 56 |  | 1 | 53 |  | 1 | 50 |  | 0 | 50 |  | 1 | 47
20 | 1b-3-9-15-18-21-28 |  | 48 |  | 0 | 48 |  | 1 | 45 |  | 0 | 45 |  | 1 | 42
21 | 1b-3-9-15-18-24-25-26-28 |  | 57 |  | 0 | 57 |  | 1 | 54 |  | 0 | 54 |  | 1 | 51
22 | 1b-3-9-15-18-24-25-27-28 |  | 58 |  | 1 | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 49
23 | 1b-6-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 0 | 51 |  | 1 | 48
24 | 1b-6-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 0 | 49 |  | 1 | 46
25 | 1b-6-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 0 | 44 |  | 1 | 41
26 | 1b-6-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 0 | 53 |  | 1 | 50
27 | 1b-6-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 0 | 51 |  | 1 | 48
28 | 1b-6-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 0 | 57 |  | 1 | 54
29 | 1b-6-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 0 | 55 |  | 1 | 52
30 | 1b-6-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 0 | 50 |  | 1 | 47
31 | 1b-6-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 0 | 59 |  | 1 | 56
32 | 1b-6-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 0 | 57 |  | 1 | 54
33 | 1c-4-10-13-19-24-25-26-28 |  | 47 |  | 0 | 47 |  | 0 | 47 |  | 1 | 45 |  | 0 | 47
34 | 1c-4-10-13-19-24-25-27-28 |  | 48 |  | 1 | 45 |  | 0 | 45 |  | 1 | 43 |  | 0 | 45
35 | 1c-4-10-13-19-22-28 |  | 36 |  | 0 | 36 |  | 0 | 36 |  | 1 | 34 |  | 0 | 36
36 | 1c-4-10-16-19-24-25-26-28 |  | 51 |  | 0 | 51 |  | 0 | 51 |  | 1 | 49 |  | 0 | 51
37 | 1c-4-10-16-19-24-25-27-28 |  | 52 |  | 1 | 49 |  | 0 | 49 |  | 1 | 47 |  | 0 | 49
38 | 1c-4-10-16-19-22-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 1 | 38 |  | 0 | 40
39 | 1c-7-10-13-19-24-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50 |  | 1 | 48 |  | 0 | 50
40 | 1c-7-10-13-19-24-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48 |  | 1 | 46 |  | 0 | 48
41 | 1c-7-10-13-19-22-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 1 | 37 |  | 0 | 39
42 | 1c-7-10-16-19-24-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54 |  | 1 | 52 |  | 0 | 54
43 | 1c-7-10-16-19-24-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 50 |  | 0 | 52
44 | 1c-7-10-16-19-22-28 |  | 43 |  | 0 | 43 |  | 0 | 43 |  | 1 | 41 |  | 0 | 43
|  |  | 63 |  |  | 62 |  |  | 59 |  |  | 59 |  |  | 56
If abetment 2 and 3 is delayed by 10 weeks then we need to creash activity 27, actvity 6, 7 and activity 18( by 3 weeks) wo meet our targets. Crashing cost will be 1288000(8000+40000+40000+1200000)
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2b to reduce critical path |  |  | Use Proposal 3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 26 |  | 0 | 26 |  | 0 | 26 |  | 0 | 26
2 | 1a-2-8-11-17-23-25-26-28 |  | 35 |  | 0 | 35 |  | 0 | 35 |  | 0 | 35
3 | 12-2-8-11-17-23-25-27-28 |  | 36 |  | 1 | 33 |  | 0 | 33 |  | 0 | 33
4 | 1a-2-8-14-17-20-28 |  | 30 |  | 0 | 30 |  | 0 | 30 |  | 0 | 30
5 | 1a-2-8-14-17-23-25-26-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39
6 | 12-2-8-14-17-23-25-27-28 |  | 40 |  | 1 | 37 |  | 0 | 37 |  | 0 | 37
7 | 1a-5-8-11-17-20-28 |  | 29 |  | 0 | 29 |  | 0 | 29 |  | 0 | 29
8 | 1a-5-8-11-17-23-25-26-28 |  | 38 |  | 0 | 38 |  | 0 | 38 |  | 0 | 38
9 | 12-5-8-11-17-23-25-27-28 |  | 39 |  | 1 | 36 |  | 0 | 36 |  | 0 | 36
10 | 1a-5-8-14-17-20-28 |  | 33 |  | 0 | 33 |  | 0 | 33 |  | 0 | 33
11 | 1a-5-8-14-17-23-25-26-28 |  | 42 |  | 0 | 42 |  | 0 | 42 |  | 0 | 42
12 | 1a-5-8-14-17-23-25-27-28 |  | 43 |  | 1 | 40 |  | 0 | 40 |  | 0 | 40
13 | 1b-3-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 1 | 46
14 | 1b-3-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 1 | 44
15 | 1b-3-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 1 | 39
16 | 1b-3-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 1 | 48
17 | 1b-3-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 1 | 46
18 | 1b-3-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 1 | 52
19 | 1b-3-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 1 | 50
20 | 1b-3-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 1 | 45
21 | 1b-3-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 1 | 54
22 | 1b-3-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 1 | 52
23 | 1b-6-9-12-18-23-25-26-28 |  | 59 |  | 0 | 59 |  | 1 | 56 |  | 1 | 51
24 | 1b-6-9-12-18-23-25-27-28 |  | 60 |  | 1 | 57 |  | 1 | 54 |  | 1 | 49
25 | 1b-6-9-12-18-21-28 |  | 52 |  | 0 | 52 |  | 1 | 49 |  | 1 | 44
26 | 1b-6-9-12-18-24-25-26-28 |  | 61 |  | 0 | 61 |  | 1 | 58 |  | 1 | 53
27 | 1b-6-9-12-18-24-25-27-28 |  | 62 |  | 1 | 59 |  | 1 | 56 |  | 1 | 51
28 | 1b-6-9-15-18-23-25-26-28 |  | 65 |  | 0 | 65 |  | 1 | 62 |  | 1 | 57
29 | 1b-6-9-15-18-23-25-27-28 |  | 66 |  | 1 | 63 |  | 1 | 60 |  | 1 | 55
30 | 1b-6-9-15-18-21-28 |  | 58 |  | 0 | 58 |  | 1 | 55 |  | 1 | 50
31 | 1b-6-9-15-18-24-25-26-28 |  | 67 |  | 0 | 67 |  | 1 | 64 |  | 1 | 59
32 | 1b-6-9-15-18-24-25-27-28 |  | 68 |  | 1 | 65 |  | 1 | 62 |  | 1 | 57
33 | 1c-4-10-13-19-24-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52 |  | 0 | 52
34 | 1c-4-10-13-19-24-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50 |  | 0 | 50
35 | 1c-4-10-13-19-22-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
36 | 1c-4-10-16-19-24-25-26-28 |  | 56 |  | 0 | 56 |  | 0 | 56 |  | 0 | 56
37 | 1c-4-10-16-19-24-25-27-28 |  | 57 |  | 1 | 54 |  | 0 | 54 |  | 0 | 54
38 | 1c-4-10-16-19-22-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
39 | 1c-7-10-13-19-24-25-26-28 |  | 55 |  | 0 | 55 |  | 0 | 55 |  | 0 | 55
40 | 1c-7-10-13-19-24-25-27-28 |  | 56 |  | 1 | 53 |  | 0 | 53 |  | 0 | 53
41 | 1c-7-10-13-19-22-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
42 | 1c-7-10-16-19-24-25-26-28 |  | 59 |  | 0 | 59 |  | 0 | 59 |  | 0 | 59
43 | 1c-7-10-16-19-24-25-27-28 |  | 60 |  | 1 | 57 |  | 0 | 57 |  | 0 | 57
44 | 1c-7-10-16-19-22-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
|  |  | 68 |  |  | 67 |  |  | 64 |  |  | 59
If abetment 2 and 3 is delayed by 15 weeks then we need to creash activity 27, actvity 6 and activity 18( by 5 weeks) wo meet our targets. Crashing cost will be 2048000(8000+40000+2000000). We will miss our target by 3 weeks

## Abetment 1,2 & 3
|  |  |  | Activity Reduction | Status | x0 | x1a | x1b | x1c | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28
|  |  | 16 weeks | Activities |  |  | 16 | 16 | 16 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  |  | 21 weeks |  |  |  | 21 | 21 | 21 | 1 | 1 | 1 | 4 | 6 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 7 | 5 | 7 | 10 | 7 | 3 | 5 | 3 | 6 | 8 | 2 | 4 | 5 | 7
|  | Proposal 1 | Proposal 2a | Proposal 2b | Proposal 2c | Proposal 3 | Proposal 4 a | Proposal 4 b | Proposal 4 c
| Activity | 27 | 5 | 6 | 7 | 18 | 20 | 21 | 22
| Crash Duration | 3 | 2 | 3 | 2 | 1*5 | 1.5 | 2.5 | 1.5
| Cost | 8000 | 40000 | 40000 | 40000 | 400000*5 | 400000 | 400000 | 400000
| Slope | 2666.6667 | 20000 | 13333.3333 | 20000 | 400000 | 266666.6667 | 160000 | 266666.6667
Cost per week
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2b to reduce critical path |  |  | Use Proposal 2c to reduce critical path |  |  | Use Proposal3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 36 |  | 0 | 36 |  | 0 | 36 |  | 0 | 36 |  | 0 | 36
2 | 1a-2-8-11-17-23-25-26-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
3 | 12-2-8-11-17-23-25-27-28 |  | 46 |  | 1 | 43 |  | 0 | 43 |  | 0 | 43 |  | 0 | 43
4 | 1a-2-8-14-17-20-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40 |  | 0 | 40
5 | 1a-2-8-14-17-23-25-26-28 |  | 49 |  | 0 | 49 |  | 0 | 49 |  | 0 | 49 |  | 0 | 49
6 | 12-2-8-14-17-23-25-27-28 |  | 50 |  | 1 | 47 |  | 0 | 47 |  | 0 | 47 |  | 0 | 47
7 | 1a-5-8-11-17-20-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39 |  | 0 | 39
8 | 1a-5-8-11-17-23-25-26-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
9 | 12-5-8-11-17-23-25-27-28 |  | 49 |  | 1 | 46 |  | 0 | 46 |  | 0 | 46 |  | 0 | 46
10 | 1a-5-8-14-17-20-28 |  | 43 |  | 0 | 43 |  | 0 | 43 |  | 0 | 43 |  | 0 | 43
11 | 1a-5-8-14-17-23-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52 |  | 0 | 52 |  | 0 | 52
12 | 12-5-8-14-17-23-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50 |  | 0 | 50 |  | 0 | 50
13 | 1b-3-9-12-18-23-25-26-28 |  | 49 |  | 0 | 49 |  | 1 | 46 |  | 0 | 46 |  | 1 | 43
14 | 1b-3-9-12-18-23-25-27-28 |  | 50 |  | 1 | 47 |  | 1 | 44 |  | 0 | 44 |  | 1 | 41
15 | 1b-3-9-12-18-21-28 |  | 42 |  | 0 | 42 |  | 1 | 39 |  | 0 | 39 |  | 1 | 36
16 | 1b-3-9-12-18-24-25-26-28 |  | 51 |  | 0 | 51 |  | 1 | 48 |  | 0 | 48 |  | 1 | 45
17 | 1b-3-9-12-18-24-25-27-28 |  | 52 |  | 1 | 49 |  | 1 | 46 |  | 0 | 46 |  | 1 | 43
18 | 1b-3-9-15-18-23-25-26-28 |  | 55 |  | 0 | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 49
19 | 1b-3-9-15-18-23-25-27-28 |  | 56 |  | 1 | 53 |  | 1 | 50 |  | 0 | 50 |  | 1 | 47
20 | 1b-3-9-15-18-21-28 |  | 48 |  | 0 | 48 |  | 1 | 45 |  | 0 | 45 |  | 1 | 42
21 | 1b-3-9-15-18-24-25-26-28 |  | 57 |  | 0 | 57 |  | 1 | 54 |  | 0 | 54 |  | 1 | 51
22 | 1b-3-9-15-18-24-25-27-28 |  | 58 |  | 1 | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 49
23 | 1b-6-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 0 | 51 |  | 1 | 48
24 | 1b-6-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 0 | 49 |  | 1 | 46
25 | 1b-6-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 0 | 44 |  | 1 | 41
26 | 1b-6-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 0 | 53 |  | 1 | 50
27 | 1b-6-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 0 | 51 |  | 1 | 48
28 | 1b-6-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 0 | 57 |  | 1 | 54
29 | 1b-6-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 0 | 55 |  | 1 | 52
30 | 1b-6-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 0 | 50 |  | 1 | 47
31 | 1b-6-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 0 | 59 |  | 1 | 56
32 | 1b-6-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 0 | 57 |  | 1 | 54
33 | 1c-4-10-13-19-24-25-26-28 |  | 47 |  | 0 | 47 |  | 0 | 47 |  | 1 | 45 |  | 0 | 47
34 | 1c-4-10-13-19-24-25-27-28 |  | 48 |  | 1 | 45 |  | 0 | 45 |  | 1 | 43 |  | 0 | 45
35 | 1c-4-10-13-19-22-28 |  | 36 |  | 0 | 36 |  | 0 | 36 |  | 1 | 34 |  | 0 | 36
36 | 1c-4-10-16-19-24-25-26-28 |  | 51 |  | 0 | 51 |  | 0 | 51 |  | 1 | 49 |  | 0 | 51
37 | 1c-4-10-16-19-24-25-27-28 |  | 52 |  | 1 | 49 |  | 0 | 49 |  | 1 | 47 |  | 0 | 49
38 | 1c-4-10-16-19-22-28 |  | 40 |  | 0 | 40 |  | 0 | 40 |  | 1 | 38 |  | 0 | 40
39 | 1c-7-10-13-19-24-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50 |  | 1 | 48 |  | 0 | 50
40 | 1c-7-10-13-19-24-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48 |  | 1 | 46 |  | 0 | 48
41 | 1c-7-10-13-19-22-28 |  | 39 |  | 0 | 39 |  | 0 | 39 |  | 1 | 37 |  | 0 | 39
42 | 1c-7-10-16-19-24-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54 |  | 1 | 52 |  | 0 | 54
43 | 1c-7-10-16-19-24-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52 |  | 1 | 50 |  | 0 | 52
44 | 1c-7-10-16-19-22-28 |  | 43 |  | 0 | 43 |  | 0 | 43 |  | 1 | 41 |  | 0 | 43
|  |  | 63 |  |  | 62 |  |  | 59 |  |  | 59 |  |  | 56
If abetment 2 and 3 is delayed by 10 weeks then we need to creash activity 27, actvity 6, 7 and activity 18( by 3 weeks) wo meet our targets. Crashing cost will be 1288000(8000+40000+40000+1200000)
[5 empty] | Use Proposal 1 to reduce critical path |  |  | Use Proposal 2b to reduce critical path |  |  | Use Proposal 3 to reduce critical path
Sl No | Paths |  | Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration |  | Activity lies on critical path' | Final Duration
1 | 1a-2-8-11-17-20-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
2 | 1a-2-8-11-17-23-25-26-28 |  | 50 |  | 0 | 50 |  | 0 | 50 |  | 0 | 50
3 | 12-2-8-11-17-23-25-27-28 |  | 51 |  | 1 | 48 |  | 0 | 48 |  | 0 | 48
4 | 1a-2-8-14-17-20-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
5 | 1a-2-8-14-17-23-25-26-28 |  | 54 |  | 0 | 54 |  | 0 | 54 |  | 0 | 54
6 | 12-2-8-14-17-23-25-27-28 |  | 55 |  | 1 | 52 |  | 0 | 52 |  | 0 | 52
7 | 1a-5-8-11-17-20-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
8 | 1a-5-8-11-17-23-25-26-28 |  | 53 |  | 0 | 53 |  | 0 | 53 |  | 0 | 53
9 | 12-5-8-11-17-23-25-27-28 |  | 54 |  | 1 | 51 |  | 0 | 51 |  | 0 | 51
10 | 1a-5-8-14-17-20-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
11 | 1a-5-8-14-17-23-25-26-28 |  | 57 |  | 0 | 57 |  | 0 | 57 |  | 0 | 57
12 | 1a-5-8-14-17-23-25-27-28 |  | 58 |  | 1 | 55 |  | 0 | 55 |  | 0 | 55
13 | 1b-3-9-12-18-23-25-26-28 |  | 54 |  | 0 | 54 |  | 1 | 51 |  | 1 | 46
14 | 1b-3-9-12-18-23-25-27-28 |  | 55 |  | 1 | 52 |  | 1 | 49 |  | 1 | 44
15 | 1b-3-9-12-18-21-28 |  | 47 |  | 0 | 47 |  | 1 | 44 |  | 1 | 39
16 | 1b-3-9-12-18-24-25-26-28 |  | 56 |  | 0 | 56 |  | 1 | 53 |  | 1 | 48
17 | 1b-3-9-12-18-24-25-27-28 |  | 57 |  | 1 | 54 |  | 1 | 51 |  | 1 | 46
18 | 1b-3-9-15-18-23-25-26-28 |  | 60 |  | 0 | 60 |  | 1 | 57 |  | 1 | 52
19 | 1b-3-9-15-18-23-25-27-28 |  | 61 |  | 1 | 58 |  | 1 | 55 |  | 1 | 50
20 | 1b-3-9-15-18-21-28 |  | 53 |  | 0 | 53 |  | 1 | 50 |  | 1 | 45
21 | 1b-3-9-15-18-24-25-26-28 |  | 62 |  | 0 | 62 |  | 1 | 59 |  | 1 | 54
22 | 1b-3-9-15-18-24-25-27-28 |  | 63 |  | 1 | 60 |  | 1 | 57 |  | 1 | 52
23 | 1b-6-9-12-18-23-25-26-28 |  | 59 |  | 0 | 59 |  | 1 | 56 |  | 1 | 51
24 | 1b-6-9-12-18-23-25-27-28 |  | 60 |  | 1 | 57 |  | 1 | 54 |  | 1 | 49
25 | 1b-6-9-12-18-21-28 |  | 52 |  | 0 | 52 |  | 1 | 49 |  | 1 | 44
26 | 1b-6-9-12-18-24-25-26-28 |  | 61 |  | 0 | 61 |  | 1 | 58 |  | 1 | 53
27 | 1b-6-9-12-18-24-25-27-28 |  | 62 |  | 1 | 59 |  | 1 | 56 |  | 1 | 51
28 | 1b-6-9-15-18-23-25-26-28 |  | 65 |  | 0 | 65 |  | 1 | 62 |  | 1 | 57
29 | 1b-6-9-15-18-23-25-27-28 |  | 66 |  | 1 | 63 |  | 1 | 60 |  | 1 | 55
30 | 1b-6-9-15-18-21-28 |  | 58 |  | 0 | 58 |  | 1 | 55 |  | 1 | 50
31 | 1b-6-9-15-18-24-25-26-28 |  | 67 |  | 0 | 67 |  | 1 | 64 |  | 1 | 59
32 | 1b-6-9-15-18-24-25-27-28 |  | 68 |  | 1 | 65 |  | 1 | 62 |  | 1 | 57
33 | 1c-4-10-13-19-24-25-26-28 |  | 52 |  | 0 | 52 |  | 0 | 52 |  | 0 | 52
34 | 1c-4-10-13-19-24-25-27-28 |  | 53 |  | 1 | 50 |  | 0 | 50 |  | 0 | 50
35 | 1c-4-10-13-19-22-28 |  | 41 |  | 0 | 41 |  | 0 | 41 |  | 0 | 41
36 | 1c-4-10-16-19-24-25-26-28 |  | 56 |  | 0 | 56 |  | 0 | 56 |  | 0 | 56
37 | 1c-4-10-16-19-24-25-27-28 |  | 57 |  | 1 | 54 |  | 0 | 54 |  | 0 | 54
38 | 1c-4-10-16-19-22-28 |  | 45 |  | 0 | 45 |  | 0 | 45 |  | 0 | 45
39 | 1c-7-10-13-19-24-25-26-28 |  | 55 |  | 0 | 55 |  | 0 | 55 |  | 0 | 55
40 | 1c-7-10-13-19-24-25-27-28 |  | 56 |  | 1 | 53 |  | 0 | 53 |  | 0 | 53
41 | 1c-7-10-13-19-22-28 |  | 44 |  | 0 | 44 |  | 0 | 44 |  | 0 | 44
42 | 1c-7-10-16-19-24-25-26-28 |  | 59 |  | 0 | 59 |  | 0 | 59 |  | 0 | 59
43 | 1c-7-10-16-19-24-25-27-28 |  | 60 |  | 1 | 57 |  | 0 | 57 |  | 0 | 57
44 | 1c-7-10-16-19-22-28 |  | 48 |  | 0 | 48 |  | 0 | 48 |  | 0 | 48
|  |  | 68 |  |  | 67 |  |  | 64 |  |  | 59
If abetment 2 and 3 is delayed by 15 weeks then we need to creash activity 27, actvity 6 and activity 18( by 5 weeks) wo meet our targets. Crashing cost will be 2048000(8000+40000+2000000). We will miss our target by 3 weeks